## Initiatives Priortization (hidden)
Responsible Team | Initiatives | Rationale | Initiative Link | Priority | Rank Order | Q1 | Q2 | Q3 | Q4
Boston | Customer access to Data API (eTMF V2) | What: Extend the platform Data_API to support direct integrations from client applications Why: eTMF integrations currently rely on support from PS Integrations team and lengthy design, development, and release projects, by offering client-facing APIs customers can more easily roll eTMF integratations driving adoption of DD Products while delivering greater compliance and reducing user-error. Measurable Outcome: DD assets can be transferred to the sponsor system in systemic industry standards according to technical specifications. | TNP-19540 | C | 8 | X
Boston | Centralized Reporting - Phase 1 | What: A technology solution that enables easy access & consumption of study data from all DrugDev products, for all trials combined into a single reportable source to monitor cross-trial progress, performance, and usage metrics. Provide cross trial reporting functionality that summarizes/combines data across all trials from existing DD products, and allows reportable metrics at the Sponsor/Study/Country/Site/Individual levels. Why: Enables DrugDev PS, Sponsors, and users of the system to gain visibility across all trials & modules concurrently. This will save time extracting insights from current functionality, and allow trial management decisions & actions to be more effectively and more often. Measurable Outcome: Drugdev products can report together from the same reporting source with combined data from all trials in a new BI reporting tool accessible from Port | TNP-19539 | H | 23 |  | X | X
London | Client Onboarding | What: Onboarding new clients onto IR and the Data Service Why: Allowing clients to take advantage of the full suite of DrugDev tools Measurable Outcome: User from Member Companies can access in-scope SUM studies and receive mastered person and study records | TNP-20718 | C | 10 | X | X
Boston | Data API V3 | What: New APIs, Expanded features of existing APIs, and performance improvements of API backend systems Why: Initial versions of the Data API were focused on building a foundation that would have it's own roadmap of enhancements and improvements beyond the narrow use-cases of V1/2. Enabling greater connectivity and automation between our Platform and those of our partners and external customers will a kay driver of scalability and delivering better experiences. Measurable Outcome: Support for new use cases, improved experience for existing clients, and ability to hand increasing numbers of API clients for 2020 and beyond. | TNP-20703
London | CTMS Integration Enhancements | What: Allow a customer to provide one feed from their CTMS to Data Services to process, and in turn DS will pass on the relevent study information to other Business Units Why: So the customers do not have to send multiple feeds containing the same data in different formates to different BUs Measurable Outcome: By providing single data feed from the sponsor’s CTMS, the integration allows a customer to leverage multiple DrugDev tools | TNP-20717 | H | 25 | X | X
London | DD Profiles Enhancements | What: Allow site users (investigators and site staff) to create and update their respective person and facility profiles Why: So that profile data can be leveraged in feasibility tools, and so thats sites are not asked the same questions for each study Measurable outcome: Profiles data can be efficiently created, updated, and leverged in other tool sets, such as eFeasibility and DQS | SCDQS-3332 | M | 30 |  | X
London | DQS Enhancements | What: Updates to the information presented in DQS Why: Improve the granularity and specificity of the information presented in DQS Measurable Outcome: DQS users have additional detail when performing study planning and site identification | SCDQS-3321 | M | 31 |  | X
Boston | Product Support and Maintanence | What: On-going support and maintenance of the existing DD Platform for clients and PS stakeholders Why: Our Platform is more than 5 years old and features lots of complexity and configurability. New issues arise with legacy features or an unforeseen complication with a recent change will require quick turnaround as they affect current clients and active Studies. Measurable Outcome: Few significant issues left unresolved for clients that negatively affect our reputation or business relationships. | TNP-20223
Boston | eSignature Enablement | What: e Signature allows users to execute complex document management end-to-end in the platform while simplifying their document storage and archiving. Why: DrugDev Spark modules involve the approval and execution of trial documents which requires the parallel maintenance of wet-ink signature versions for filing purposes.e Signature implementation enables these modules with eSig capabilities to fully consolidate document management to in-system execution, aligning with regulatory best practices and filling the current gap of out-of-system wet ink document versions. Measurable Outcomes: (1) eSig should be enabled via configuration when necessary throughout the platform (2) Ability to create a PDF with electronic signature and pass PDF to vTMF (3) eSig activity should be traceable in audit trail (4) System should support single or multiple e-sig as part of document negotiation process (5) System should require PI eSig before assigning trainings in the D-Log (6) System should require PI e-Sig and reasons for change when updating trainings in the D-Log | TNP-19519 | C | 4 | X | X
Boston | Site Activation ¦ Activation Reports | What: Provide reporting in the Site Activation Module by grouping documents, workflows, and displaying cycle times Why: Providing better site activation reporting would allow sponsors to have increased visibility into their trial’s activation process. Configurability with the module is powerful but can hinder summary reporting of activity within a trial from sites in different countries. Measurable Outcome: A new Pending Action report that is able to group documents and workflows and provide better Summary environment to Activation clients. | TNP-19553 | C | 11 | X
Boston/London | Performance and Scalability | What: DD Spark needs to manage the growth through projection in 2019 and in addition handling the current state of affairs. We must drive platform performance beyond a breaking point. Why: To improve the quality of existing infrastructure and ensure applications remain scalable Measurable Outcome: Infrastructure remains resilient and application modules are scalable for future releases and growth through 2019 and beyond. | TNP-19483 |  |  | X | X
Boston | Search Enhancements | What: Replace the technology our platform utilizes for Search Why: Our current search functionality is limited in scope as the underlying implementation has been slow to manage current data loads, leading to delays and poor user experience Measurable Outcome: Existing Search features and functionality are maintained with a new, more performant and scalable technology able to handle the projected growth for 2019 and beyond | TNP-19542 | H | 17 | X | X
London | SIP and Supplemental IR Enhancements | What: Extending IR and Supplemental IR to support SIP and Member Company enhancements Why: Adding new members and introducing new search functionality for facility and person-facility improves the result set returned to the Member Company Measurable Outcome: SIP or the Member Company only needs to run one single query when searching instead of multiple queries (or a single coplex query) | TNP-20714 | H | 18 | X | X
Boston | Site Activation Enhancements ¦ Launch Study and Country Activation | What: Extend the Functionality of our Site Activation modules (Checklist, Workflow, Document Library) to the Country and Study level. Why: To reflect the full scope of documents, information, roles and responsibilities necessary to account for Study Start-up and Activation processes. Measurable Outcome: Site Activation module can support Documents/Workflow actions/Checklist progress with existing Site-level functionality to the entire Study or Country level. UAT | TNP-20722 | C | 13 |  | X
Boston | Site Activation Enhancements ¦ Onboard Configuration Optimization | What: To accommodate our desired growth we need to optimize this process by examine our current features and limitations and deliver enhancements. Why: Existing Site Activation features and modules are configured on a Study by Study basis and required significant up-front analysis and configuration that is difficult to replicate in many studies, even those that are similar or executed by the same team or Sponsor. Measurable outcome: Confidently able to onboard clients or partners that are adding dozens of Studies using Start Up per month. | TNP-20503 | C | 15 |  | X
Boston | Site Activation Enhancements ¦Cross Trial Documents | What: Enable Site Activation artifacts including documents and templates to be used by multiple trails by setting it up once Why: To reduce inefficiencies and duplication of documents and workflows resulting in errors and delayed onboarding Measurable Outcome: enable efficiencies through cross-trial documents, scalability through cross trial templates | TNP-20541 | H | 19 |  | X
Boston | Site Activation Enhancements ¦Cross Trial Templates | What: Build Cross Trial Template app to create, manage, and store configurations of Checklists items and workflows Why: for PS to be able to support our clients as they scale Measureable Outcome: Checklist items and workflow configuration app | TNP-20542 | C | 14 |  | X
Boston | Site Activation Enhancements¦Enhancements | What: Enhance Site Activation to address new market needs/ client requirements associated to workflow design addressing onboarding, configuration, and notification pain points Why: The Site Activation functionality of the DD Platform is powerful and can be configured to support diverse workflows, however difficulty in system configuration and limited flexible in notification options can cause onboarding and adoption to be hindered. Measurable Outcome: Setup and configuration of the Checklist and Workflow is streamlined to be support faster setup, notification options have been expanded to offer greater flexibility while support complex work processes. | TNP-19485 | M | 27 |  | X
London | Site and User Management | What: Allow a customer to manage their Site and User Management processes using DrugDev Technology Why: A platform that provides a suite of tools that allows a study to be managed seamlessly Measurable Outcome: By providing one single feed from CTMS a customer can login and access all applications with one username and password to manage a study | TNP-20712 | C | 7 | X | X
Boston/London | SSO Enhancements | What: Provide support and configuration updates needed to enable and accelerate adoption and integrations with IQVIA clients and systems Why: IQVIA adoption is a key goal for the entire DrugDev organization both through CRO PT of trials and closer integrations to IQVIA systems, tools, and key teams. To fully integrate with these systems some additional work will be required on DD Platforms and applications to account for existing architecture, systems and processes. Measurable Outcome: Tight integrations and an achievable delivery roadmap to address roadblocks and difficulties in adoption. | TNP-19528 | H | 26 |  | X
London | SSO Integration [ClinTech Applications] | What: Integrate ClinTech SSO ecosystem with the Enterprise SDA solution Why: Simplifies the overall SSO ecosystem within IQVIA Measurable Outcome: Users can access ClinTech applications across data stores (Keycloak, iNet) | TNP-20875 | H |  | X | X
London | SSO Integration [External] ¦ Site Based Users | What: Integrate ClinTech SSO ecosystem with the Enterprise SDA solution Why: Simplifies the overall SSO ecosystem within IQVIA Measurable Outcome: Users can access ClinTech applications across data stores (Keycloak, iNet) | TNP-20720 | H | 20 | X | X
London | SSO Integration [Internal] ¦ Sponsor Based Users | What: Enable sponsor-based users to use their company credentials to authenticate to Spark Why: Simplifies the process of accessing multiple sponsor applications for sponsor-based users Measurable Outcome: Sponsor-based users can authenticate with company credentials | TNP-20716 | H | 21 | X | X
Boston | Trial Archive | What: Implement a new process(es) to archive data related to a closed study to address the current lack of process to systemically archive study data from production database Why: Simplified process is needed to reduce strain on PS and Ops and improve responsiveness to clients. Measurable Outcome: The implementation should result in secure, validated process to request, action, and execute a full archive of all data related to a tenant and archived data is stored in a searchable and retrieve-able format. | https://drugdev.atlassian.net/browse/TNP-20540 | L | 36 | X
Boston | Unified Product Experience: Navigation | What: Improve the user experience across all modules by creating a navigation framework that will seamlessly bring together modules in the Spark family Why: Users don't know where they are, or how to get to other parts of spark, leading to a confusing, disjointed experience. Measurable Outcome: Users know where they are and feel like they are working within a single system, regardless of where they are, so that we are truly a "one stop clinop shop". They see only what is relevant to them, and can easily get to where they need to go. They do not have to think about how they get from one place to another. | https://drugdev.atlassian.net/browse/TNP-19544 | M | 34 | X
Boston | Training Enhancements ¦ Additional Features | GT | TNP-20715 | L | 35 |  | X
Boston | Training Enhancements ¦ Production Release Support | What: Continue to address client facing bugs that potentially compromise workflow Why: sLamina spent 11 points on features, 21 on client-facing bugs Measurable Outcome: sLamina has story point bandwidth to address client support tickets | TNP-20707 | M | 28 |  | X
Boston | Training Enhancements ¦ Technical Debt | What: Implement functionality in the LMS Catalog and in Platform to enable sponsor users to handle complex content management use cases while seamlessly managing end user assignment and cross-trial credit. Why: Janssen contractual obligation; allows LMS product to deliver consistent value throughout the trial lifecycle and establishes LMS product as significantly best positioned for trial management use cases. Reduces burden of manual record reconciliation on PS, increases accuracy of records, and allows for scalability of cross-trial LMS with volumes expected from sponsor-wide use. Measurable Outcome: External users are able to create linked records of updated training content in the LMS catalog. They are able to distribute this content and update training assignments in platform. The catalog allows for the upload of multiple languages and formats of a training and allows users to "hack" the credit sync job to maximize utility. All reports track the specific training version completed. | TNP-20557 | M | 29 |  | X
Boston | Training Enhancements¦ Delegation Log V2 | What: Improve on Delegation of Authority Log v1, adding ability to require PI approval, course status, improved email notifications. Electronic Delegation Log will include PI approval of user-task assignments per site and calculated qualification date of a task for a user, based on training completion dates. Why: (1) Tracking trial-specific tasks and assigning training separately leads to confusion about what training is required and fulfilled per user where sites may have incorrect information on what training is required. It is cumbersome to map and track all of the data (2) Sponsors have difficulty determining if site staff are assigned and trained to perform trial-specific tasks where sites may be unprepared to complete the trial, while sponsors are unaware Measurable Outcomes: (1) At a Trial-level, delegation log tasks can be created and mapped to courses (2) At a Site-level, users can be assigned to tasks, and have trainings automatically assigned. | TNP-19529 | C | 3 |  | X
Boston | Training Enhancements¦ Delta Training | What: Enable sponsor users to employ summary of change trainings for versioned cross-trial training content. Why: Reduce training burden on site users by allowing them to take a smaller summary of change training when they have completed the previous version of versioned training content. Measurable Outcome: Summary of change trainings can be added to versioned cross-trial training content in the catalog; trainees assigned to new cross-trial versions that have completed the previous training version are served the smaller SoC training content instead of the full version. | TNP-20708 | M | 32 |  | X
Boston | Training Enhancements¦ eSignature with Delegation Log | GT | TNP-20709 | C | 5 |  | X | X | X
Boston | Training Enhancements¦ Protocol Training | What: Support versioning of cross-trial protocol training content. Why: Ensure that site users are served only the appropriate content that their site is approved for and reduce the administrative overhead for site managers of managing protocol amendments for their sites. Measurable Outcome: Catalog users can version protocol training content to support protocol amendments; site trainees are served only the appropriate protocol version training content within the trial for their site's IRB-approved version. | TNP-20710 | M | 33 |  | X
Boston | Training Enhnacements ¦ Equivalence | What: Implement functionality in the LMS Catalog and in Platform to enable sponsor users to handle complex content management use cases while seamlessly managing end user assignment and cross-trial credit. Why: Janssen contractual obligation; allows LMS product to deliver consistent value throughout the trial lifecycle and establishes LMS product as significantly best positioned for trial management use cases. Reduces burden of manual record reconciliation on PS, increases accuracy of records, and allows for scalability of cross-trial LMS with volumes expected from sponsor-wide use. Measurable Outcome: External users are able to create linked records of updated training content in the LMS catalog. They are able to distribute this content and update training assignments in platform. The catalog allows for the upload of multiple languages and formats of a training and allows users to "hack" the credit sync job to maximize utility. All reports track the specific training version completed. | TNP-20107 | C | 1 | X | X
Boston | Training Enhnacements ¦ Versioning | What: Implement functionality in the LMS Catalog and in Platform to enable sponsor users to handle complex content management use cases while seamlessly managing end user assignment and cross-trial credit. Why: Janssen contractual obligation; allows LMS product to deliver consistent value throughout the trial lifecycle and establishes LMS product as significantly best positioned for trial management use cases. Reduces burden of manual record reconciliation on PS, increases accuracy of records, and allows for scalability of cross-trial LMS with volumes expected from sponsor-wide use. Measurable Outcome: External users are able to create linked records of updated training content in the LMS catalog. They are able to distribute this content and update training assignments in platform. The catalog allows for the upload of multiple languages and formats of a training and allows users to "hack" the credit sync job to maximize utility. All reports track the specific training version completed. | TNP-20252 | C | 2 |  | X
Boston | Unified Product Experience | What: Improve the user experience across all modules by creating a navigation framework and design system that will seamlessly bring together modules in the Spark family Why: Users don't know where they are, or how to get to other parts of spark, leading to a confusing, disjointed experience. Measurable Outcome: Users know where they are and feel like they are working within a single system, regardless of where they are, so that we are truly a "one stop clinop shop". They see only what is relevant to them, and can easily get to where they need to go. They do not have to think about how they get from one place to another. | TNP-19544 |  |  | X

## BO Priortization (hidden)
Initiative | BO Priority (C,H,M,L) | EPIC ID | BO Summary | BO- Description | Proposed UAT Rollout | Story Stubs | BO- T-Shirt Size (Dev) | Development Sequence | Scrum Team | Product Lead | Dev Lead | Dev and QA Complete | In Scope
Training Enhancements ¦ Versioning | C | TNP-20235 | Training Enhancements ¦ Versioning¦ Support Versioning of Catalog Content | What: Implement functionality in LMS catalog to support and manage versioning of training content Why: Janssen contractual obligation; Eliminate manual workarounds for creating holistic training records; scale for enterprise use; reduce end to end initial site qualification and re-qualification Measurable Outcome: Catalog Users can upload updated versions of training content and link the updated content to equivalent relationships | July | 1. Prompt user to update equivalences when uploading versions 2. Catalog: Uploading Training Version 3. Document architectural plan for versioning 4. Ability specify trial access to version | L |  | sLamina | GT/ Peter | Brett Miller | May | -
Training Enhancements ¦ Versioning | C | TNP-20234 | Training Enhancements ¦ Versioning ¦ Trigger Changes to Platform Assignments based on catalog versioning | What: Implement functionality in platform to support distribution of training versions Why: Janssen contractual obligation; Eliminate manual workarounds for creating holistic training records; scale for enterprise use; reduce end to end initial site qualification and re-qualification Measurable Outcome: Training Admins can manage the present and future distribution of training versions | July | 1. Document architectural path for versioning assignment 2. Front End Support to display assignment changes 3. Front End Support to specify if retake is needed from trainee 4. Training Admin ability to indicate if training retake is needed from trainee 5. When a trainee is assigned new training version, previous version will be replaced 6. Training Admin can mark a training version as a mandatory retake for all trainees 7. Training Admin can mark a training version as a mandatory retake for trainees based on training status | L |  | sLamina | GT/ Peter | Brett Miller | June | -
Training Enhancements ¦ Versioning | C | TNP-20072 | Training Enhancements ¦ Versioning ¦ Update Reports for Versioning | What: Update catalog and platform reporting to reflect version completed for training content Why: Janssen contractual obligation; Eliminate manual workarounds for creating holistic training records Measurable Outcome: Catalog Users can track training version in LMS and platform reports. | July | 1. Update Training Certificates for Versioning 2. Update Catalog Report for Versioning 3. Update Platform Reports for Versioning 4. Update Platform Reports to reflect retake and qualification carry over | L |  | sLamina | GT/ Peter | Brett Miller | June | -
eSignature Enablement | C | TNP-19522 | eSig Enablement ¦ Implementation ¦ API Admin/Auth | What: Enable platform to connect to DocuSign API and make/receive calls and responses, as well as receive and handle errors appropriately. Why: This basic functionality is a pre-req to being able to do any further eSig work, including integrating it into specific modules, allowing for reporting and processing of signatures. Measureable Outcome: | June | - Set up OAuth token requests from DocuSign - Configure OAuth settings on per-environment basis - Create boilerplate error-handling code - Establish document purging parameters - Define process for DevOps to roll this project out - Setup DocuSign Accounts for each platform Enviornment - Ensure this work is scriptable | M |  | EPL | Nick S/Max | Alex Bromley | April
eSignature Enablement | C | TNP-20853 | eSign Enablement ¦ Implementation ¦ SQS Setup and Admin | What: AWS SQS tool will be able to handle the response / request / status updates from the Docusign API Why: A queue will be a better way to handle the async nature of the the response and status details of Envelope Creation, Doc Conversion, and Signing completion/rejection. Measurable Outcome: SQS Infrastructure and cloudformation scripts to create in all environments. | April | -SQS Infrastructure -Deployment scripts (cloudformation) -Platform endpoint to communicate with SQS | S |  | EPL | Nick S/Max | Alex Bromley | April
eSignature Enablement | C | TNP-20656 | eSig Enablement ¦ Implementation ¦ Password Management | What: User needs to be able to create/manage their "Signing Password". Why: 21CFRpart11 compliance requires users to have and enter a "signing password". Therefore, we need them to be able to create/edit thier password. For regulatory purposes, this PW should be subject to all existing complexity and rotation requiremtns. Measureable Outcome: User can create/edit their PW. User is forced to update their PW. PW must be complex. | June | - Create data model to support signing passwords (account-level) - Enforce password complexity and rotation requirements - Create admin screen to manage passwords - Give users the ability to update their password/"forget" PW system - Implement system to handle failed Signing PW attempts - [Not included in estimate. Need to investigate requirements here, would become its own Epic] Meet and adhere to requirements around locking user out of primary account based on failed PW attempts | S |  | EPL | Nick S/Max | Alex Bromley | May
eSignature Enablement | C | TNP-20654 | eSig Enablement ¦ Implementation ¦ Envelope Creation | What: Allow platform to create envelopes at DocuSign, with specifications around what document and what signers. Furthermore, user notifications and functionality to support graceful failures and error message are major components here. Why: Before eSig can be integrated into any module or existing process, Spark needs the ability to create and manage envelopes via API calls. Measureable Outcome: Envelope can be created, edited, "destroyed" programmatically. Users are notified accordingly. | June | - Create envelopes - Identify signers - Set up platform to read Amazon SQS about envelope status (post-format conversion) - Create programmatically-generated signature page to be added to doc when uploaded - Add signers to existing envelope - Ensure deactivated users are not able to eSign documents - Handle envelope creation failures | M |  | EPL | Nick S/Max | Alex Bromley | May
Training Enhancements ¦ Delegation Log V2 | C | TNP-19536 | Training Enhancements ¦ Delegation Log V2 ¦ DLV2 Feature Flag | What: Create clear separation of DLV2 work from existing DLV1 functionality. Why: Janssen requires a full 30 day UAT of new features and functionality before they will agree to it being deployed to their Studies in Production. We need to ensure new features of V2 do not change functionality of live in-progress studies in production. Measurable Outcome: Feature Flag on the Tenant level to allow DLV2 work to disabled by default and only affected Networks that is it configured for. | April | -Create a feature flag for DLv2 Work - Ensure guardrails exist to place all DLv2 behind the flag | M (2) |  | Crusher | Saunders/GT Max | Andrew Ullmann | April
eSignature Enablement | C | TNP-20663 | eSig Enablement ¦ Implementation ¦ D-Log Versioning | What: Update the Delegation Log to be in multiple status and versions. These will include the statuses Pending/Being Reviewed/Approved. Why: To Account for the new eSignature feature of the Delegation Log the system needs to differenatied between a Pending and Approved DL to ensure the Training are only assigned when they should be. Measureable Outcome: An assigner can create Assignments that do not create trainings until the DL is signed. | July | - Create states of DLog: Pending, Out for Signature, Approved - Restrict changes to DLog in "out for signature" state - Future changes to DLog in Approved state create a new version of the DLog - Signers can decline to sign "out for signature" document; document moves back to "Pending" - Sender can cancel a DLog sent for eSig and moves back to "Pending" - Training assignments from pending DLog are not created if the site is configured to use eSignature - Handle migration of existing Logs (assigned tasks) | M (1) |  | Crusher | Saunders/GT Max | Andrew Ullmann | June
eSignature Enablement | C | TNP-20854 | eSig Enablement ¦ Implementation ¦ Upload Document to Envelope | What: Allow platform to upload document to Docusign envelope Why: Before eSig can be integrated into any module or existing process, Spark needs the ability to create and manage envelopes via API calls. Measureable Outcome: Async document upload, support for large files, and error handling | June | - Upload document asynchronously - Uploading documents larger than 25MB -Concerns around scalability of the upload/conversion/response process | S |  | EPL | Nick S/Max | Alex Bromley | May
eSignature Enablement | C | TNP-20655 | eSig Enablement ¦ Implementation ¦ Signing Ceremony | What: Allow users to actaully execute their eSig on a document. This is where we need to prompt them to enter their "signing password" (and create one if they don't already have one). At this point, we need to make sure data is logged for future auditing and that our system can handle the use case of the signer "declining to sign" the document. Why: Once the envelope is created, allowing users to sign it and save that record is the next step in the process. Measureable Outcome: User can sign or not sign, and is authenticated properly for 21CFRpart11 compliance. | June | - Present signer(s) with signing URL - Open Docusign UI in iFrame - Set up WebHooks to notify platform when signature takes place - Authenticate signing user with signing password details - Handle decline to sign | S |  | EPL | Nick S/Max | Alex Bromley | June
eSignature Enablement | C | TNP-20590 | eSig Enablement ¦ Implementation ¦ Site Activation Admin & Signing | What: An embedded eSignature feature that allows designated users the ability to review and provide compliant electronic signature to any Activation document. This signature will proceed the approval process and tracked with history and audit trail. Why: The Site Activation process faciliates the exchange, collection and approval of crucial Study documents, some of these documents require wet or compliant electronic signature. Delivering an embedded eSig experience within our tools to collect and approval documents will accelerate activation cycle times and improve the end-user experience. Measureable Outcome: The ability to configure approval workflows and Checklist documents to use eSignature and specify which users/roles are able to sign specific documents. Support for email notifications to inform users that a signature is needed. | June | - New Transition Type: eSignature - Connect checklist items with eSig Transition Type to eSignature API - Allowable actors of eSig transition are able to itnitiate signing session with the checklist item document through the API - Signed document is added to checklist item as latest version - Signer can decline to sign, which will leave the workflow in the same state - Show a "Ready to Sign" URL to the Signing user which when clicked will create the envelope and dynamically replace the URL with the signing URL - (NICE TO HAVE) For checklist items that are classified with supported eTMF artifacts, embed the eSignature date in Date of Signature form field - (NICE TO HAVE) Simplified workflow notification with eSignature call to action | M |  | EPL | Nick S/Max | Alex Bromley | June
eSignature Enablement | C | TNP-20659 | eSig Enablement ¦ Implementation ¦ D-Log Admin | What: Enable a sponsor-level admin to determine which study sites can have an eSig Delegation log, as well as who/what user type can review and sign the D-Log. Why: Not all sites will have this ability, and only certain people can be responsible for progressing the D-Log workflow. Measureable Outcome: PIs at some sites are able to review and eSig sign a D-Log | June | - Crusher, maybe - Allow admin to enable/disable e-Sig per site (REQ-LMS-0460) - Specify who can submit a DL setup for review by PI (who gets to click Send for Review?) (REQ-LMS-0480) - Specify who can execute E-Sig (U_11S_0070) | M |  | EPL | Nick S/Max | Alex Bromley | July
eSignature Enablement | C | TNP-20591 | eSig Enablement ¦ Implementation ¦ D-Log Signing Experience | What: An embedded eSignature feature that allows a PI or other designated users the ability to view a snapshot of a completed Delegation Log for their sites (Personnal:Tasks) what when signed will assign those users to the appropriate trainings for their Tasks. Why: The Delegation of Authority Log is a crucial Trail document that allows the participating Site to specify which of their Trial Participants will be responsible for completing each Task within the Study. The content of this Log is owned by the Site and their PI, it's crucial that the Sponsor gets the PI's signature in order to validate the log. Measureable Outcome: A Site Monitor is able to request a PI to eSig and approve a Delegation Log, system should only create training assignments once the PI signs and approves their Log. | June | - Log time and document of e-signature (U_11S_0010, U_11S_0030,REQ-LMS-0490,U_11S_0040) - Require PI signature when task assignments are updated - User receives notification from Spark that a document requires signature - Create training assignments only once DL has been moved to approved state (REQ-LMS-0470) - Signed DLog is stored in appropriate folder in Document Library w/ eTMF classifications if network is using classifications - For DLog, successful completion will transition DLog to approved state - Handle Signing ceremony errors - For DLog, unsuccessful completion will transition DLog to pending state - Handle declined envelopes | M |  | EPL | Nick S/Max | Alex Bromley | July
eSignature Enablement | C | TNP-20623 | eSig Enablement ¦ Implementation ¦ Reporting/eTMF/Audit Trail | What: Enable Superusers and Admins to use Audit Trail as a basic form of reporting on eSig and ensure extracted documents have appropriate eTMF tagging. Why: The ability to audit who signed what when, and/or see a list of eSigs processed over a period of time is a key requirement for this project. This solution is the precursor to, and enables future, expansions of eSig reporting capabilities. Measureable Outcome: The ability to search and filter on types of transactions in the AT to find any (or a specific) eSig event. Doc Library contents that are exported for eTMF purposes that contain eSigs are tagged/categorized appropriately. | June | - Normal audit trail logging will be maintained for eSignature documents - Ability to filter for eSignature events in audit trail - Define any new metadata tags needed due to the document being e-signed - Signed document metadata added and visible in the document library | S |  | EPL | Nick S/Max | Alex Bromley | June
Training Enhancements ¦ Delegation Log V2 | C | TNP-20349 | Training Enhancements ¦ Delegation Log V2 ¦ Trainee Qualification Progress | What: Implementation of changes to DL to display task qualification progress of site trainees. Why: Better enable site monitors and operational stakeholders to easily track progress and identify delays to accelerate qualification times. Measurable Outcome: DL frontend displays training qualification progress for each site trainee in Assign Tasks view. | July | Ability to view training module progress Ability to view task progress as rollup of trainings Visual indicator for when trainee is out of compliance Capture of task qualification date | M (3) |  | Crusher | GT/ Saunders | Andrew Ullmann | July
Training Enhancements ¦ Delegation Log V2 | C | TNP-20744 | Training Enhancements ¦ Delegation Log V2 ¦Qualification Bundle Notifications | What: Group relevant notifications for site trainees and site monitors into single, regularly cadenced notifications. Why: Keep users informed of upcoming tasks and relevant delays across trainings without fatiguing them. Measurable Outcome: Assignment and due date notifications for site trainees are consolidated into digest notifications; updates of trainee status at affiliated sites are grouped into digest notifications for monitors. | July | Group assignment and due date notifications into single digest notification for trainees Group trainee qualification status updates into single digest notification for monitors Send at config-specific time cadence (including Create notification for trainees to be sent one day before due date) | M (4) |  | Crusher | GT/ Saunders | Andrew Ullmann | June
Training Enhancements ¦ Delegation Log V2 | C | TNP-20745 | Training Enhancements ¦ Delegation Log V2 ¦ Qualification Due Dates | What: Re-orient training due date notifications to key off of user-provided dates. Why: Update due date notifications to map to real world use cases. Measurable Outcome: Site monitors can input site and user due dates to schedule deadline-based notifications. | July | Allow site manager to provide trainee-specific qualification due date Allow site manager to provide site-wide qualification due date (Do we need this? Where is it being used?) | S (5) |  | Crusher | GT/ Saunders | Andrew Ullmann | June
Training Enhancements ¦ Delegation Log V2 | C | TNP-20746 | Training Enhancements ¦ Delegation Log V2 ¦ Ad-Hoc Notification Trigger | What: Allow site monitors to ad-hoc trigger notifications to be sent to site trainees. Why: Provide an in-system means for monitors to remind site users of incomplete/overdue trainings. Measurable Outcome: Site monitors can trigger site trainee notifications via the delegation log frontend. | July | Site manager can trigger pending notifications for any trainee at one of their affiliated sites | S (7) |  | Crusher | GT/ Saunders | Andrew Ullmann | July
Training Enhancements ¦ Delegation Log V2 | C | TNP-20748 | Training Enhancements ¦ Delegation Log V2 ¦ UAT and Release Plan | What: Develop a plan to support the UAT for Janssen and sync it with our Release Plan of the work. Why: Janssen requires a full 30 day UAT of new features and functionality before they will agree to it being deployed to their Studies in Production. For Enhancements to existing features like DL v2 we'll be to account for these in our Release Plan. Measurable Outcome: Clear plan with dates, dependencies and risks agreed between Dev/Product/PS team/DevOps | July | -Make a plan | S (9) |  | Crusher | GT/ Saunders | Andrew Ullmann | July
Site Activation Enhancements ¦ Launch Study and Country Activation | C | TNP-19986 | Study, Country Checklist Functionality Site Activation Enhancements ¦ Launch Study and Country Activation ¦ Extention of Checklist functionality | What: Extend Checklist functionality to Study and Country activation levels Why: To assist sponsors in the full-scope of a Study Start-up Measurable Outcome: Complete extention of Checklist and workflow functionality at new Study and Country levels | July | Implement site blacklist for checklist families - data model Implement site blacklist for checklist families - UI Create UI for displaying Multi-Level Checklist for network admin user Remove Dashboard View Update Workflow dropdown on Checklist Item Assign Countries and their Sites to ChecklistFamily | L |  | 000 | Evelyn V, Nick Saunders | Nathan Willson | April
Training Enhancements ¦ Delegation Log V2 | C | TNP-20747 | Training Enhancements ¦ Delegation Log V2 ¦ Delegation Log Report Updates | What: Expand the scope of the delegation log report to include more information about task qualification and qualification progress across sites. Why: Ensure the site-specific delegation log report is oriented around primary use case of task qualification progress; provide a trial-wide view into task qualification. Measurable Outcome: Site-specific delegation log report includes task qualification columns; a task qualification report exists containing information for all sites using delegation log in a trial. | July | - Update delegation log report to include columns for task qualification status and qualification date - Simplified DL report for eSignature - Create new trial-wide report that uses delegation log report format scoped to all sites on a trial - For sites with versioned Logs include only approved ones | S (6) |  | Crusher | GT/ Saunders | Andrew Ullmann | June
Site Activation Enhancements ¦ Launch Study and Country Activation | C | TNP-19490 | Site Activation Enhancements ¦ Launch Study and Country Activation ¦ Create Workflows | What: Extend Workflow functionality to Study and Country activation levels Why: Workflow functionality to the Study and Country Levels to support multi-level checklists Measurable Outcome: Complete Workflows at Study and Country levels | July | View Workflow Templates by Level Create/Edit Checklist Workflow States & Transitions for Study, Country Ability to export Workflow chart | M |  | 000 | Evelyn V, Nick Saunders | Nathan Willson | April
Site Activation Enhancements ¦ Launch Study and Country Activation | C | TNP-19992 | Site Activation Enhancements ¦ Launch Study and Country Activation ¦ Export Checklist | What: Extend current export functionality site activation reporting to include new Study and Country level checklist and checklist item reports. Why: To support Sponsor needs of current SA reporting to the Study and Country levels Measurable Outcome: Complete export abilities at the Study and Country level | July | Export a multi- Level Checklist XML Export A List of Study Checklist Items Export A List of Country Checklist Items Export A List Of Checklist Completion Status by Study Export A List Of Checklist Item Workflows Status By Country Export A List Of Checklist Item Workflows Status By Study Import a multi-level checklist | S |  | 000 | Evelyn V, Nick Saunders | Nathan Willson | June
Site Activation Enhancements ¦ Launch Study and Country Activation | C | TNP-19952 | Site Activation Enhancements ¦ Launch Study and Country Activation ¦ Permissions | What: Extend Permissions settings to Study and Country Why: To ensure correct users and roles and access and act on appropriate checklist items Measureable outcome: Users can access applicable documents in the DocLib | July | SPIKE - Investigate model changes to implement Secondary Actor with Permissions in the Workflow Assign Secondary Actor with Permissions in the Workflow Edit Study Type Role to include the ability to act on behalf of Countries | M |  | 000 | Evelyn V, Nick Saunders | Nathan Willson | June
Site Activation Enhancements ¦ Launch Study and Country Activation | C | TNP-20866 | Site Activation Enhancements ¦ Launch Study and Country Activation ¦ Secondary Actor | What: Create secondary actor Why: Users can act on behalf of other users Measureable outcome: Ability to for a secondary actor to act on a checklist item | July | Checklist Items - Validate permissions work at study/country SPIKE: User permissions for multi-level Checklists and Workflows Ability to use Study roles for Study level Checklist and Workflow Ability to use Country roles for Country level Checklist and Workflow Assign Study/Country Actors on Transitions - redundant of existing workdlow ? | M |  | 000 | Evelyn V, Nick Saunders | Nathan Willson | June
Site Activation Enhancements ¦ Launch Study and Country Activation | C | TNP-19944 | Site Activation Enhancements ¦ Launch Study and Country Activation ¦ Enhance Document Library | What: Enhance Doc Library for Study and Country Why: To ensure new checklist level documents are stored in the correct corresponding folders Measurable outcome: Complete and correct folder settings at Study and Country levels | July | Country Folder Creation Rules User Can Access Study Folders And Select Documents Country Folder Contains Country Level Documents from Checklist Study Folder Contains Study Level Documents from checklist | S |  | 000 | Evelyn V, Nick Saunders | Nathan Willson | June
Site Activation Enhancements ¦ Launch Study and Country Activation | C | TNP-20037 | Site Activation Enhancements ¦ Launch Study and Country Activation ¦Checklist Dependency Trigger | What: Allow for checklist item documents to be sent to lower level checklist items Why: To increase checklist efficiencies by sending a completed parent checklist item automatically to a checklist checklist item Measurable Outcome: Complete functionality of a checklist item trigger | July | Select higher level trigger checklist item Notify child items when parent item is completed Pull completed documents from higher level checklist items using lower level transition | M |  | 000 | Evelyn V, Nick Saunders | Nathan Willson | May
Search Enhancements | C | TNP-20593 | NSE ¦ Implementation ¦ Final Rollout | What: Potential carryover of work on Elasticsearch from Q1 2019 Why:Measureable Outcome: Final release of this project, enabling more efficient search functionality | April | - TBD - TBD | S |  | EPL | Nick S/Max | Alex Bromley | April
Product Support and Maintanence | C | TNP-20877 | Product Support and Maintanence ¦ Versioning and Equivalence¦ UAT and Release Plan | What: Establish client UAT and go-to-production plans for both long-running versioning and equivalence functionality. | July |  | S |  | sLamina | GT/ Peter | Brett Miller | June | -
Product Support and Maintanence | H | TNP-20731 | Product Support and Maintanence ¦ Crusher Q2 Maintanence | What: Provide support and needed bug fixes to PS and clients for the features and modules that Crusher is responsbile for including Audit Trail/Member Management and other components. Why: Crusher is responsbile for key features and components of the Platform and needs to be responsive to issues and urgent requests that arise. Measurable Outcome: Key issues prioritized and addressed in a reasonable timeframe. | June |  | M (8) |  | Crusher | Saunders | Andrew Ullmann | June
Performance, Scalability and Maintainence | H | TNP-20442 | Performance, Scalability and Maintainence¦ Re Architect - Automation Framework | What: Enhance Automation reporting to better understand the results and resource utilization of the automation Why: To reduce manual efforts in results gather and determine areas that are low performing Measurable Outcome: Faster analysis time of the results | May | 1. Automatic zapi - a zephr API that allows us to store all of our automation tests results into zephyr. 2. Expanded slack messaging from jenkins | M |  | SKYNET | Josh Greenwood | Jeremy | May
Performance, Scalability and Maintainence | L | Epics in Note | Performance, Scalability and Maintainence¦ Write Manual Test Cases | What: Write team backlog test cases Why: Reduce backlog Measurable Outcome: Reduce our backlog of 15 K to hit all of the code and validation | June | 1. Audit high priority legacy functionality (Most used - TBD by PS) 2. Write high priority legacy functionality test cases 3. Audit medium priority legacy functionality (Most used - TBD by PS) 4. Write medium priority legacy functionality test cases 5. Audit low priority legacy functionality (Most used - TBD by PS) 6. Write low priority legacy functionality test cases | XL |  | SKYNET | Josh Greenwood | Maria | April
Performance, Scalability and Maintainence | L | EPICs in Note | Performance, Scalability and Maintainence¦ Build out automation for modules not in development | What: Build out the automation for features and modules not in active development Why: Reduce manual regression work Measurable Outcome: For the quarter - | June | 1. Automate high priority legacy functionality (Most used - TBD by PS) 2. Automate medium priority legacy funcationality 3. Automate low priority legacy functionality | XL |  | SKYNET | Josh Greenwood | Jeremy | April
Performance, Scalability and Maintainence | M | TNP-20443 | Performance, Scalability and Maintainence¦ Re Architect - Automation Framework | What: Extract Spark specific automation code from the framework Why: So other applications automation can be built off of the core framework Measurable Outcome: More IQVIA offices leveraging the Boston Framework | May | 1. Extract active record instrances 2. Create bit bucket directories | S |  | SKYNET | Josh Greenwood | Jeremy | April
Note on C34: TNP-20420 TNP-20421 TNP-20422 TNP-20423 TNP-20424 TNP-20425 TNP-20426 TNP-20427 TNP-20428 TNP-20429 TNP-20430 TNP-20431 TNP-20432 TNP-20433 TNP-20434 TNP-20435 TNP-20436 TNP-20437 TNP-20438 TNP-20439
Note on C35: TNP-20420 TNP-20421 TNP-20422 TNP-20423 TNP-20424 TNP-20425 TNP-20426 TNP-20427 TNP-20428 TNP-20429 TNP-20430 TNP-20431 TNP-20432 TNP-20433 TNP-20434 TNP-20435 TNP-20436 TNP-20437 TNP-20438 TNP-20439

## Q2 Boston Tech (hidden)
Initiative | U-I | Phase | I- Client Impact | BO Priority (C,H,M,L) | Rank Order | EPIC ID | BO Summary | BO- Description | BO-Del Month | BO- Customer Rollout | Story Stubs | BO- T-Shirt Size (Dev) | Scrum Team | Q2: In Scope or Out of Scope | Product Lead | Dev Lead | Status (Jan 30) | Comments (where needed) | Boston Dependency
Performance, Scalability and Maintainence | x | Concept/Discover/Ideation 3 slides |  | M | P1 | https://drugdev.atlassian.net/browse/TNOPS-2211 | Performance, Scalability and Maintainence¦Redis CDI | What: Use Redis for Caching Why: Redis provides a better centralized way to cache data, Remove cache from a shared file server Measurable Outcome: Concept Discovery Ideation | April | April |  |  | BackBone |  | Biren Shaw | Biren Shaw
Performance, Scalability and Maintainence |  | Concept/Discover/Ideation 3 slides |  | H | P2 | https://drugdev.atlassian.net/browse/TNOPS-2212 | Performance, Scalability and Maintainence¦Redis CDI | What:Jenkins is an open-source continuous integration and continuous delivery tool, which can be used to automate building, testing, and deploying software. Why: Rearchitect installation to scale Measurable Outcome: Running many build plans in parallel, automatically spinning up and removing agents to save costs and distributing the load. | April | April |  |  | BackBone |  | Biren Shaw | Biren Shaw
Performance, Scalability and Maintainence |  | Analysis |  | L | P3 | https://drugdev.atlassian.net/browse/TNOPS-2213 | Dockerization of Platform¦SFTP Structure | What: Re-architect sFTP Solution for Professional Services Why: Suport customer sFTP access Measurable Outcome: Implemenatation | June | June |  | M | BackBone |  | Biren Shaw | Biren Shaw
Performance, Scalability and Maintainence |  | Concept |  | H | P4 | https://drugdev.atlassian.net/browse/TNOPS-2214 | Database Architecture | What: Complete a product governance deck with completed concept, discovery , ideation and phase plan for introducing high value scalibity epics. Why: Evaluate the current state and target state of DB architecture Measurable Outcome: Product Governance Deck & Product Confluence Page | April | April |  | Time Box | BackBone |  | Biren Shaw | Rao
Performance, Scalability and Maintainence |  | Implementation | Novartis | C | 1 | https://drugdev.atlassian.net/browse/TNOPS-1482 | Moving from ECS to EKS - Currently Assigned to John | What: Manage a fleet of docker containers Why: EKS (Kubernetes) provides better orchestration features as copmared to ECS. Measurable Outcome: All product components, including core platform, will be running in auto-scaling Docker containers. | June | June | 1. Rewrite play books 2. Rebuild infrastructure 3. Containerize 4. Convert to aurora 5. Define auto scaling policy | how many sprints? 6 sprints, 2 dev | BackBone |  | Biren Shaw | Biren Shaw |  | Create docker image for platform- maybe John can provide an image | Must go after search- so we can remove the old search code, more so the libra office libraries
Performance, Scalability and Maintainence |  | Implmentation | External Impact | H | 2 | https://drugdev.atlassian.net/browse/TNOPS-2215 | Performance, Scalability and Maintainence¦Adopt Redis | What: Use Redis for Caching Why: Redis provides a better centralized way to cache data, Remove cache from a shared file server, provide code coverage metrics as required by our clients Measurable Outcome: Scalable and in deployments the cache will require no cache directory management | May | May | 1. Add Redis to the infrastructure 2. Update platform configs's 3. Promote to Dev 4. Promote to QA 5. Promote to Prod | 1 sprint, 1 dev | BackBone |  | Biren Shaw | Biren Shaw
Performance, Scalability and Maintainence |  | Implementation |  | H | 3 | https://drugdev.atlassian.net/browse/TNOPS-2216 | Performance, Scalability and Maintainence¦High Value DB Maintenance Epics- May | What: Identify & Prioritize High Value Work - Indexes, Queries Why: Align work to dev teams during quarterly planning, optimize for faster performance Measurable Outcome: Product Governance Deck & Product Confluence Page | May | May | 1 Optimize Tables 2. Add missing indexes 3. Drop unused Indexes | 1 dev, 2 sprints | BackBone |  | Biren Shaw | Rao |  |  | Team Time Boxes- Coordinate fixes with releases and high priority QA work and testing.
Performance, Scalability and Maintainence |  | Implementation |  | H | 4 | https://drugdev.atlassian.net/browse/TNOPS-2217 | Performance, Scalability and Maintainence¦High Value DB Maintenance Epics - June | What: Identify & Prioritize High Value Work - Indexes, Queries Why: Align work to dev teams during quarterly planning, optimize for faster performance Measurable Outcome: Product Governance Deck & Product Confluence Page | June | June | 1 Optimize Tables 2. Add missing indexes 3. Drop unused Indexes | 1 dev, 2 sprints | BackBone |  | Biren Shaw | Rao |  |  | Team Time Boxes- Coordinate fixes with releases and high priority QA work and testing.
Performance, Scalability and Maintainence |  | Implementation |  | M | 5 | https://drugdev.atlassian.net/browse/TNOPS-2218 | Dockerization of Platform¦Dockerize ETMF | What: Dockerize the ETMF Application Why: Scale and Maintain the application as part of the Platform Measurable Outcome: Implementation of a docker container | May | May |  | S | BackBone |  | Biren Shaw | Biren Shah
Performance, Scalability and Maintainence |  | Analysis |  | H | p0 | TNP-20368 TNP-20369 TNP-20370 TNP-20371 | Automation Training | What: Training regarding running automation tests locally on their long running branches Why: Prevent integration issues when merging feature branch to development branch. Measurable Outcome: Reduce development breaking automation tests and related manual work | May | May | 1. 1 hour meeting on how to run automaiton 2. 2 hour meeting on virtual box setup | Time Box - 3 hours | SKYNET |  | Josh Greenwood | Jeremy
Performance, Scalability and Maintainence |  | Analysis |  | C | P2 | TNP-20441 | Jenkins CDI | What: Allow Automation runs to be distibuted across multiple Jenkins workers Why: To allow for faster automation executions Mesuarble Outcomes: Execution time reduction by over 50% | April | April | 1. Enable automatic ZAPI kickoff to store test results in Zephyr 2. Expand slack messaging from Jenkins server | How many sprints? 2 sprints , 1 dev | SKYNET |  | Josh Greenwood | Jeremy
Performance, Scalability and Maintainence |  | Analysis |  | M | P6 | TNP-20441 | Re Architect - Automation Framework | What: Allow Automation to kickoff a second execution of initial failures Why: To remove false negatives Mesuarble Outcomes: Less time analyzing test results | May | May | 1. Store multiple results on Jenkins 2. Automate kickoff of automation when failing test cases exist 3. Create Parsing method for reading initial and rerun resluts | How many sprints? 3 sprints , 1 dev | SKYNET |  | Josh Greenwood | Jeremy
Performance, Scalability and Maintainence |  | Analysis |  | C | P7 | TNP-20447 TNP-20453 TNP-20454 TNP-20455 TNP-20456 TNP-20457 | MVP of Golden Database | What: We need to build out data for testing servers Why: to support robust testing and load testing Measurable Outcome: Clean stable data | April | April | 1. Create neccessary test data on testing server 2. Capture data on sql dump 3. Create volumization scripts for load testing 4. Capture extra large datasets in sql dumps 5. Capture data from automation setup scripts in sql dump | How many sprints? 2 sprints , 4 dev | SKYNET |  | Josh Greenwood | Josh Greenwood
Performance, Scalability and Maintainence |  | Training |  | H | P8 | TNP-20368 TNP-20369 TNP-20370 TNP-20371 | Automation Training | What: Teach Manual QA to program the automation Why: Enable the manual QA to contribute to the automation effort Measurable Outcome: Faster Automation development | May | June | 1. 1 hour scrum meeting 2. 2 hour follow up for environment and virtual box setup | Time Box - 3 hours | SKYNET |  | Josh Greenwood | Josh Greenwood |  | Virtual Box | Virtual Box
Performance, Scalability and Maintainence |  | Analysis |  | H | P9 | TNP-20441 | Re Architect - Automation Framework | What: Allow Automation runs to multiple instance on a single worker node Why: To allow for faster automation executions Mesuarble Outcomes: Execution time reduction by over 50% | May | May | 1. Move from ECS to EKS 2. Update automation to be flaggable for X number of workers 3. Implement Selenium grid into the automation |  | SKYNET |  | Josh Greenwood | Jeremy
Performance, Scalability and Maintainence |  | Analysis |  | H | P10 | TNP-20533 | Centralize testing and deployments for integration team | What: Integrate the Integrations Team to DD Platform Why: Reduce dev ops overhead and centralized testing and development Measurabel Outcome: Reduce overhead | June | June |  |  | SKYNET |  | Josh Greenwood | Jeremy
Performance, Scalability and Maintainence |  | Implementation | Novartis | H | 1 |  | Load testing bugs & code issues | What: Automation Engineers will Establish and Run performance tests Why: To determine low performing areas of the application and those at risk of bringing down production Measurable Outcome: Faster response times and less errors for customers | April | June | 1. Develop and run scripts for Site Creation 2. Develop and run scripts for User Registration 3. Develop and run scripts for Elastisearch 4. Develop and run scripts for Audit Trail 5. Build out load test environment | TBD | SKYNET |  | Josh Greenwood | Alex B |  |  | EPL- Need a PO conversation - Requires cross team planning. Set up meeting 2 hours
Performance, Scalability and Maintainence |  | Implementation | Novartis | H | 2 |  | Load testing bugs & code issues | What: Developer implement performance fixes Why: To prevent the application from crashing and preventing users from accessing it Measurable Outcome: Faster response times and less errors for customers | April | May | 1. Implement performance fixes | TBD | SKYNET |  | Josh Greenwood | TBD |  |  | All teams may be involved
Performance, Scalability and Maintainence |  | Implementation |  | H | 3 | TNP-20442 | Re Architect - Automation Framework | What: Enhance Automation reporting to better understand the results and resource utilization of the automation Why: To reduce manual efforts in results gather and determine areas that are low performing Measurable Outcome: Faster analysis time of the results | May | May | 1. Automatic zapi - a zephr API that allows us to store all of our automation tests results into zephyr. 2. Expanded slack messaging from jenkins | How many sprints? 2 sprints , 1 dev | SKYNET |  | Josh Greenwood | Jeremy |  |  | Jeremy is assigned, he is not on a scrum team
Performance, Scalability and Maintainence |  | Implementation |  | L | 7 | TNP-20420 TNP-20421 TNP-20422 TNP-20423 TNP-20424 TNP-20425 TNP-20426 TNP-20427 TNP-20428 TNP-20429 TNP-20430 TNP-20431 TNP-20432 TNP-20433 TNP-20434 TNP-20435 TNP-20436 TNP-20437 TNP-20438 TNP-20439 | Build out automation for modules not in development | What: Build out the automation for features and modules not in active development Why: Reduce manual regression work Measurabel Outcome: For the quarter - | April | June | 1. Automate high priority legacy functionality (Most used - TBD by PS) 2. Automate medium priority legacy funcationality 3. Automate low priority legacy funcationality | How many sprints ? 6 sprints, 4 dev | SKYNET |  | Josh Greenwood | Jeremy
Performance, Scalability and Maintainence |  | Implementation |  | M | 4 | TNP-20443 | Re Architect - Automation Framework | What: Extract Spark specific automation code from the framework Why: So other applications automation can be built off of the core framework Measurable Outcome: More IQVIA offices leveraging the Boston Framework | April | May | 1. Extract active record instrances 2. Create bit bucket directories | How many sprints ? 6 sprints, 4 dev | SKYNET |  | Josh Greenwood | Jeremy |  |  | Jeremy is assigned, he is not on a scrum team
Performance, Scalability and Maintainence |  | Implementation |  | M | 5 | TNP-20449 TNP-20450 TNP-20451 TNP-20452 | Critical automation problems that occur during development | What: Fix broken automation that is a result of downstream changes to platform Why: So the automation can continue to function and provide regression testing Measurable Outcome: All test cases can be run | April | June | 1. Determine root cause of failures 2. Implement fix | How many sprints ? 6 sprints, 4 dev | SKYNET |  | Josh Greenwood | Jeremy
Performance, Scalability and Maintainence |  | Implementation ( No per se concept but broken down by team) |  | L | 6 | TNP-20420 TNP-20421 TNP-20422 TNP-20423 TNP-20424 TNP-20425 TNP-20426 TNP-20427 TNP-20428 TNP-20429 TNP-20430 TNP-20431 TNP-20432 TNP-20433 TNP-20434 TNP-20435 TNP-20436 TNP-20437 TNP-20438 TNP-20439 | Write Manual Test Cases | What: Write team backlog test cases Why: Reduce backlog Measurabel Outcome: Reduce our backlog of 15 K to hit all of the code and validation | April | June | 1. Audit high priority legacy functionality (Most used - TBD by PS) 2. Write high priority legacy functionality test cases 3. Audit medium priority legacy functionality (Most used - TBD by PS) 4. Write medium priority legacy functionality test cases 5. Audit low priority legacy functionality (Most used - TBD by PS) 6. Write low priority legacy functionality test cases | How many sprints ? 6 sprints, 4 dev | SKYNET |  | Josh Greenwood | Maria

## London Q-Plan (hidden)
Team | Initiative | Q4 Initiative Description | Priority (C, H, M, L) | Ranking | Category | Phase | Workstream | Client Impact | Quarterly Business Objectives | Target Delivery Month | Customer Impact Month | Epic Summary | Epic Description | Story Summary | Epic Priority (C, H, M, L) | T-Shirt Size | Story Points | Scrum Team | In Scope or Out of Scope | Product Lead | Status (Oct 30) | Comments (where needed)
London | Test Automation CTMS | Continued test automation for all tools. CTMS is initial priority. Some technical difficulties w/ VPN. | H | 3 | Internal Commitment | Implementation |  |  |  | December | NA |  |  |  |  | L |  |  | In | Mahdi | On track
London | Site SSO (Core) | Implement the logic and user flows related to site-based users of Spark, accounting for multiple sponsor IDPs, so that we will be ready to deliver on enterprise customer commitments in Q1/19. | C | 4 | External Commitment | Design & Implementation | SSO | Janssen/ Novartis | Implement the logic and user flows related to site-based users of Spark, accounting for multiple sponsor IDPs, so that we will be ready to deliver on enterprise customer commitments in Q1/19. | Q1 | March | Logic and user flows related to site-based users of Spar | Implement routing logic for 7 user flow scenarios to direct user to appropriate authentication method. Update existing API to include optional sponsor ID for new clients (Boston). |  |  | M |  |  |  | Mike |  | Will commence once concept discovery is complete
London | Test Automation for IR (Q1) | Continued test automation for all tools. IR is the second priority. Some technical difficulties w/ VPN. | M | 5 | Internal Commitment | Concept/ Implementation |  |  |  | TBD | TBD |  |  |  |  | XL |  |  |  | Colin | On track
London | Front End User Management Tools | All trial users of the enterprise systems are managed via CTMS (Source of Truth) via integration enable user access and user management via a central system | C | 8 | External Commitment | Discovery | CTMS | Janssen | Complete discovery to inform the Front End User Management Scope so that Clients (Janssen) to address issues on user reconciliation/ migration as needed and enable single sourced user management includes creation of new users and deactivate existing users | November | November | Complete discovery to inform the Front End User Mangement Scope | As a Product Manager, I want to know the strategy to implement Front End User Management Tools so that I am aware of its impact on context of end to end body of work that needs to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  | H | XS |  |  | In | Kirithika | On track
London | Front End User Management Tools | All trial users of the enterprise systems are managed via CTMS (Source of Truth) via integration enable user user access and user management via a central system | C | 8 | External Commitment | Ideation | CTMS | Janssen | Complete Ideation Phase (Complete initial analysis in order to confirm design and architecture direction and refine estimates ) associated with FrontEnd User Management | December | December | Complete Ideation Phase (Complete initial analysis in order to confirm design and architecture direction and refine estimates ) | As a Product Manager, I want to complete an analysis in order to confirm design and architecture direction and refine estimates to inform Front End User Management Tools so that I am able to work on its design to inform the story grooming and estimates for the product feature. Address the following: 1. List of epics 2. Refined "epic level" estimates and risks 3. Storymaps or N/A 4. Prototype and/or high level arch direction or N/A 5. Experience design or N/A |  |  | S |  |  | In | Kirithika | Deferred | To progress in Q1 planning. Product lead currently Mahdi, TBC
London | Novartis Go-Live on SUM (site and non-site) | Novartis launch on SUM | C | 8 | External Commitment | Implementation | CTMS/Data Service | Novartis | Novartis launch on SUM | October | October | Novartis launch on SUM | Novartis launch on SUM | NA | NA | S |  |  | In | Colin | On track
London | Curation Tool changes for SIP 3.1 | Make changes in curation tool to allow a Golden Facility to be created without it needing to be associated to a person | H | 14 | External Commitment | Implementation | CTMS/Data Service/IR | IDB/TrC Members | Complete development and testing | October | March | IR for SIP R3.1 | IR for SIP R3.1 |  | H | XS |  |  | In | Bryan | On track
London | IQVIA CTMS and SSO | Resolve email address mismatch issues between IQVIA's AND, their CTMS feed, Spark and Keycloak, so that IQVIA users can authenticate via IQVIA's PingFederate IDP. | H | 14 | External Commitment | Discovery | SSO/ CTMS | IQVIA | To connect Spark/Keycloak to IQVIA's PingFederate environment and define user management processes | November | Q2 | Connect Spark/Keycloak to IQVIA's PingFederate environment | Convert exceptions to iqvia.com local part based on exceptions file Update logic in CTMS import process to convert email domain Conduct manual cleanup of existing quintiles accounts in Spark Confirm update to SAML response from IQVIA IDP and turn on SSO |  |  | M |  |  | In | Mike | On track | Implementation not until Q2 (blocked on FE User Management tools)
London | DQS - Indexer Optimisation | Undertake optimisation on the indexer for DQS to improve searching and updating of results | H | 16 | Internal Commitment/Performance | Concept | CTMS/Data Service | IDB/TrC Members | Updating people or facilities in a real-time (or overnight T+1) basis as they are added to Data Services. This will include making them searchable by criteria within DQS | January | NA | DQS - Indexer Optimisation | Updating people or facilities in a real-time (or overnight T+1) basis as they are added to Data Services. This will include making them searchable by criteria within DQS |  |  | M |  |  | In | Mahdi | On track | NVS's IDP not ready until Q2
London | Infrastructure - Ubuntu upgrade | Upgrade all servers to latest version of Ubuntu. This ensures we comply with our audit guidelines by running up to date software with latest patches. | H | 17 | Internal commitment | Implementation | CTMS/Data Service/IR | IDB/TrC Members | Upgrading to latest version of Ubuntu to ensure our compliance with NFR and audit requirements | March | NA | Ubuntu upgrade | Upgrading to latest version of Ubuntu to ensure our compliance with NFR and audit requirements |  | NA | XL+ |  |  | In | Houman | Done
London | Profiles - Connect Tech Debt | Front End Technical debt: All components will need to be re-factored and upgraded. This is first major upgrade required to keep F.E. up to date since and compliance since launch | H | 18 | Internal commitment | Implementation | CTMS/Data Service/IR | IDB/TrC Members |  | Q1 | NA | Profiles - Connect Tech Debt | Front End Technical debt: All components will need to be re-factored and upgraded. This is first major upgrade required to keep F.E. up to date since and compliance since launch |  | TBC | XL+ |  |  | In | Mahdi | Deferred | Vertex has not come back with a formal request for delivery at this time.
London | IR for SIP 3.1 | Complete development and testing for new IR endpoints for SIP R3.1 In Q4, we will be assisting Cognizant integration testing in the new IR endpoints for multiple city and state searching and filtering . | H | 20 | External Commitment | Implementation | CTMS/Data Service/IR | IDB/TrC Members | Completing development and supporting testing by SIP for Q1 2019 release | October | October | Completing development and supporting testing by SIP for Q1 2019 release | Completing development and supporting testing by SIP for Q1 2019 release |  | H | XS |  |  | In | Colin | Done
London | Site SSO (JAN) | Lay the groundwork for implementing Site SSO for Janssen in Q1 | M | 21 | External Commitment | Implementation | SSO | Janssen | Configure Keycloak environments to connect with Exostar on behalf of Janssen | Q1 | March | Configure Keycloak environments to connect with Exostar on behalf of Janssen | Configure Keycloak environments to connect with Exostar on behalf of Janssen | [6 empty] | Mike | On track | JAN still determining desired timing
London | Site SSO (NVS) | Lay the groundwork for implementing Site SSO for Novartis in Q2 | M | 22 | External Commitment | Implementation | SSO | Novartis | Configure Keycloak environments to connect with Novartis's external IDP (Ping implementation) | Q1 | April | Configure Keycloak environments to connect with Novartis's external IDP (Ping implementation) | Configure Keycloak environments to connect with Novartis's external IDP (Ping implementation) | [6 empty] | Mike | On track
London | User management for eConsent | Enable eConsent module to send User Management data and set up users of the platform | M | 28 | Internal Commitment | Concept | CTMS/Data Service | Internal | To allow Consent to send User Management data and set up users of the platform | Q1 | TBD | Allow Consent to send User Management data and set up users of the platform | Enable eConsent module to send User Management data and set up users of the platform | [6 empty] | Mike | On track
London | Feasibility SSO | In partnership with CTOS team, complete Concept and Design to prepare for Implementation of Profiles in the tool in Q2 | L | 31 | Internal Commitment | Concept | SSO | Novartis | Complete Concept and Discovery phases, so that we are prepared to support CTOS with implementation in Q2 | Q1 | Q1 | Complete Concept and Discovery Phase | Support CTOS with implementation in Q2: Complete Concept and Discovery | [6 empty] | Mike | On track
London | Sponsor SSO (VRTX) | N/A - likely Q1 implementation | L | 33 | External Commitment | Implementation | SSO | Vertex | To connect Spark/Keycloak to Vertex's internal IDP | TBD | TBD | Configure Keycloak environments to connect with Vertex's internal IDP | Configure Keycloak environments to connect with Vertex's internal IDP | [6 empty] | Mike | Tracking to delivery - with some risks/actions
London | Profiles SSO | To connect Spark/Keycloak to Connect/DD Profiles so that investigators can create/manage profile information from Spark | L | 34 | Internal Commitment | Concept/Design | SSO | Investigators | Complete Concept and Design so that we are prepared for Implementation in Q1 | Q1 | Q2 | Complete Concept and Design so that we are prepared for Implementation in Q1 | Complete Concept and Design so that we are prepared for Implementation in Q1 | [6 empty] | Mike | Deferred | Timing will be some time after IQVIA CTMS and SSO delivery
London | DQS SSO | To connect Spark/Keycloak to DQS so that users can authenticate using their company credentials | L | 35 | Internal Commitment | Concept/Design | SSO | IDB/TrC Members | Complete Concept and Design so that we are prepared for Implementation in Q1 | Dec/Jan | NA | To connect Spark/Keycloak to DQS | To connect Spark/Keycloak to DQS so that users can authenticate using their company credentials | [6 empty] | Mike
London | IQVIA CTMS Sponsor | Changes in support of splitting Data Source vs. Customer Secret Token. Investigate whether needs to be completed in Q4 | C | New | Internal | Concept |  |  |  | TBD | TBD Q4 | [8 empty] | ??? | On track
London | eConsent SSO | Connect eConsent into the KeyCloak SSO. Ideally happen w/ IQVIA SSO. Question: implications for Lilly Identity Hub | [7 empty] | Not Q4 | Not Q4 | [8 empty] | Mike | Tracking to delivery - with some risks/actions | We'll need to make changes to the tests/files once the CTMS organisation changes and Facility from SUM to Site endpoint changes are in (current tests will fail, and the scenarios will no longer be totally true)
London | CTMS integration organisation and role enhancement | Enhancement to send Non-site organisations and roles (at the non-site organisation level) to the Portal |  |  |  | Implementation | CTMS/Data Service |  |  | TBD | [5 empty] | M |  |  | In | Mahdi/Colin | At risk | Waiting for BI to confirm their timeline
London | BI Onboarding CTMS | Primarily BA work, but on-boarding will require changes to create VPD, importer, DQS, sharing rules, etc. Colin to determine timing | C |  | External Commitment | Concept (XS) |  |  |  | TBD | TBD |  |  |  |  | XS |  |  |  | Colin | Deferred | Focusing on CTMS integration at present
London | CS-API: Move Facility details from SUM to Site endpoint | This is urgently required in order to keep the data consistent, which is needed for Safety. Ideally, we get it done for v1.5.5, but if there isn't enough time to test it, this can wait. If it waits, there has to be some data cleaning afterwards. But again better well tested than rushing it and putting us in a worse situation than before. | C |  |  | Implementation | CTMS/Data Service/IR |  |  | November | N/A |  |  |  |  | S |  |  | In | Colin | On track
London | CS-API SUM | We need to be able to accept real-time api calls in the future. Likely starting with NVS, but the implementation should be customer-agnostic | M |  | Internal Commitment | Concept/Discovery | CTMS/Data Service/IR |  |  | December | H1 19 likely |  |  |  |  | S |  |  | In | Colin

## Resource Planning (hidden)
[7 empty] | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20
Team | Team Members | Names | Capacity Consideration | Percent Effort | Business Objective |  | Jan S1 | Jan S2 | Feb S1 | Feb S2 | Mar S1 | Mar S2 | Apr S1 | Apr S2 | May S1 | May S2 | June S1 | June S2
Slamina | Dev |  |  |  | Site Activation Enhancements¦ Activation Reports - Pending Action Report
Dev
Dev
Dev
QA
QA
QA
QA
[5 empty] | Finish Activation Reporting | S
Slamina |  |  |  |  | Training Enhancements¦ Versioning and Equivalence V1 ¦ Equivalence: Catalog Functionality | L
| Dev | Peter G | 1 |  |  |  | S1: 100%; S2: 50%; S3: 25%; S4: 25%
| Dev | Frank | 1 |  |  |  | S1: 10%; S2: 10%; S3: 10%; S4: 10%
| Dev | Luke I | 1 |  |  |  | S1: 10%; S2: 10%; S3: 10%; S4: 10%
| Dev | George | 1 |  |  |  | S1: 10%; S2: 100%; S3: 100%; S4: 100%
| QA | Julie | 1
| QA | Jhonsi | 1
Slamina |  |  |  |  | Training Enhancements¦ Versioning and Equivalence V1 ¦ Equivalence: Catalog Equivalents | M
| Dev | Peter G | 1 |  |  |  | S4: 50%; S5: 50%; S6: 10%
| Dev | Frank | 1
| Dev | Luke I | 1 |  |  |  | S4: 90%; S5: 90%; S6: 90%
| Dev | George | 1
| QA | Julie | 1 |  |  |  | S4: 50%; S5: 50%; S6: 50%
| QA | Jhonsi | 1 |  |  |  | S4: 50%; S5: 50%; S6: 50%
Slamina |  |  |  |  | Training Enhancements¦ Versioning and Equivalence V1 ¦ Equivalence: Equivalenence End User Choice | M
| Dev | Peter G | 1 |  |  |  | S2: 50%; S3: 25%; S4: 50%
| Dev | Frank | 1 |  |  |  | S2: 90%; S3: 90%; S4: 90%
| Dev | Luke I | 1
| Dev | George | 1
| QA | Julie | 1 |  |  |  | S2: 50%; S3: 50%; S4: 50%
| QA | Jhonsi | 1 |  |  |  | S2: 50%; S3: 50%; S4: 50%
Slamina |  |  |  |  | Training Enhancements¦ Versioning and Equivalence V1 ¦ Reporting: End User Reports | s
| Dev | Peter G | 1
| Dev | Frank | 1 |  |  |  | S5: 50%; S6: 50%
| Dev | Luke I | 1
| Dev | George | 1 |  |  |  | S5: 100%; S6: 100%
| QA | Julie | 1 |  |  |  | S5: 50%; S6: 50%
| QA | Jhonsi | 1 |  |  |  | S5: 50%; S6: 50%
Sum Check | [6 empty] | S2: 600%; S3: 600%; S4: 600%; S5: 600%; S6: 600%
|  | Peter |  |  |  |  | S2: 100%; S3: 50%; S4: 125%; S5: 50%; S6: 10%
|  | Frank |  |  |  |  | S2: 100%; S3: 100%; S4: 100%; S5: 50%; S6: 50%
|  | Luke I |  |  |  |  | S2: 10%; S3: 10%; S4: 100%; S5: 90%; S6: 90%
|  | George |  |  |  |  | S2: 100%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
|  | Julie |  |  |  |  | S2: 50%; S3: 50%; S4: 100%; S5: 100%; S6: 100%
|  | Jhonsi |  |  |  |  | S2: 50%; S3: 50%; S4: 100%; S5: 100%; S6: 100%
[8 empty] | 410% | 360% | 625% | 490% | 450%
[5 empty] | e Signature Enablement ¦ Ideation (Alex) | S | S2: 500%; S3: 500%; S4: 500%; S5: 500%; S6: 500%
EPL | Dev | Erol
| Dev | Dele
| Dev | Demetrius
| QA | Andrey | 0.5
| QA | Irina | 0.5 |  |  |  | S5: 25%; S6: 25%
[5 empty] | eTMF V2¦ Ideation- Technical Specification | S
EPL | Dev | Erol
| Dev | Dele |  |  |  |  | S1: 50%; S2: 50%
| Dev | Demetrius
| QA | Andrey | 0.5
| QA | Irina | 0.5
[5 empty] | eTMF V2¦ Implementation | M
EPL | Dev | Erol |  |  |  |  | S1: 75%; S2: 75%; S3: 100%; S4: 50%; S5: 50%; S6: 50%
| Dev | Dele |  |  |  |  | S1: 50%; S2: 50%; S3: 100%; S4: 100%; S5: 50%; S6: 50%
| Dev | Demetrius
| QA | Andrey | 0.5 |  |  |  | S1: 50%; S2: 50%; S3: 50%; S4: 50%; S5: 50%; S6: 50%
| QA | Irina | 0.5
[5 empty] | New Search Engine¦ Implementation | M
EPL | Dev | Erol
| Dev | Dele
| Dev | Demetrius |  |  |  |  | S1: 50%; S2: 100%; S3: 100%
| QA | Andrey | 0.5
| QA | Irina | 0.5
[5 empty] | New Search Engine¦ Concept, Discovery and Ideation | XS
EPL | Dev | Erol
| Dev | Dele
| Dev | Demetrius |  |  |  |  | S1: 50%
| QA | Andrey | 0.5
| QA | Irina | 0.5
[5 empty] | eTMF V1 ¦ Maintenance and Support | XS
EPL | Dev | Erol |  |  |  |  | S1: 25%; S2: 25%
| Dev | Dele
| Dev | Demetrius
| QA | Andrey | 0.5
| QA | Irina | 0.5
[5 empty] | New Search Engine¦ Implementation.OPS | M
EPL | Dev | Erol |  |  |  |  | S4: 50%; S5: 50%; S6: 50%
| Dev | Dele
| Dev | Demetrius |  |  |  |  | S4: 50%; S5: 50%; S6: 50%
| QA | Andrey |  |  |  |  | S3: 25%; S4: 25%; S5: 25%; S6: 25%
| QA | Irina (proper permissioning) |  |  |  |  | S3: 100%; S4: 100%; S5: 100%; S6: 100%
[5 empty] | e Signature Enablement ¦ Implementation | S
EPL | Dev | Erol
| Dev | Dele |  |  |  |  | S5: 50%; S6: 50%
| Dev | Demetrius |  |  |  |  | S5: 50%; S6: 50%
| QA | Andrey
| QA | Irina (proper permissioning)
Check Sum |  | Erol |  |  |  |  | S1: 100%; S2: 100%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
|  | Dele |  |  |  |  | S1: 100%; S2: 100%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
|  | Demetrius |  |  |  |  | S1: 100%; S2: 100%; S3: 100%; S4: 50%; S5: 100%; S6: 100%
|  | Andrey |  |  |  |  | S1: 50%; S2: 50%; S3: 75%; S4: 75%; S5: 75%; S6: 75%; S9: 0; S10: 0
|  | Irina (proper permissioning) |  |  |  |  | S1: 0; S2: 0; S3: 100%; S4: 100%; S5: 125%; S6: 125%
[5 empty] | Site and User Management ¦ Analysis of change of email of a user and impact | XS
Crusher | Dev | Andrew | Dependency on UK |  |  |  | S2: 25%; S3: 25%
| Dev | Ken
| Dev | Raphael
| Dev | Kevin
| QA | Zach
| QA | Kara ?
[5 empty] | Performance and Scalability ¦ Audit Trail V2 and V3 Rollout | L
Crusher | Dev | Andrew | Feature Feedback May result in more work |  |  |  | S1: 50%; S2: 50%
| Dev | Ken |  |  |  |  | S1: 100%; S2: 100%
| Dev | Raphael |  |  |  |  | S1: 100%; S2: 100%
| Dev | Kevin |  |  |  |  | S1: 100%; S2: 100%
| QA | Zach |  |  |  |  | S1: 100%; S2: 100%
| QA | Kara ? |  |  |  |  | S1: 100%; S2: 100%
| Unidentiied QA | [5 empty] | S1: 100%; S2: 100%
| Unidentiied QA | [5 empty] | S1: 100%; S2: 100%
| Unidentiied QA | [5 empty] | S1: 100%; S2: 100%
[5 empty] | Performance and Scalability ¦ Processing Scale | S
Crusher | Dev | Andrew
| Dev | Ken |  |  |  |  | S3: 50%; S4: 25%
| Dev | Raphael |  |  |  |  | S3: 50%; S4: 25%
| Dev | Kevin |  |  |  |  | S3: 0; S4: 100%
| QA | Zach
| QA | Kara ?
[5 empty] | Training Enhancements¦Delegation Log V2 ¦ Concept, Discovery and Ideation | S
Crusher | Dev | Andrew |  |  |  |  | S2: 25%; S3: 25%
| Dev | Ken
| Dev | Raphael
| Dev | Kevin
| QA | Zach
| QA | Kara ?
|  |  | plug extra capacity |  | Training Enhancements¦Delegation Log V2 ¦ Implementation
Crusher | Dev | Andrew
| Dev | Ken |  |  |  |  | S3: 50%; S4: 50%; S5: 100%; S6: 100%
| Dev | Raphael |  |  |  |  | S3: 25%; S4: 75%; S5: 100%; S6: 100%
| Dev | Kevin |  |  |  |  | S5: 100%; S6: 100%
| QA | Zach |  |  |  |  | S3: 25%; S4: 25%; S5: 75%; S6: 75%
| QA | Kara ? |  |  |  |  | S3: 25%; S4: 25%; S5: 75%; S6: 75%
[5 empty] | Trial Archive ¦Concept and Discovery | s
Crusher | Dev | Andrew | 1 week february
| Dev | Ken
| Dev | Raphael
| Dev | Kevin | 2 weeks february
| QA | Zach
| QA | Kara ?
[7 empty] | 600% | 600% | 600% | 600% | 600% | 600%
Check Sum |  | Andrew |  |  |  |  | S1: 50%; S2: 100%; S3: 50%; S4: 0; S5: 0; S6: 0
|  | Ken |  |  |  |  | S1: 100%; S2: 100%; S3: 100%; S4: 75%; S5: 100%; S6: 100%
|  | Raphael |  |  |  |  | S1: 100%; S2: 100%; S3: 75%; S4: 100%; S5: 100%; S6: 100%
|  | Kevin |  |  |  |  | S1: 100%; S2: 100%; S3: 0; S4: 100%; S5: 100%; S6: 100%; S9: 0; S10: 0
|  | Zach |  |  |  |  | S1: 100%; S2: 100%; S3: 25%; S4: 25%; S5: 75%; S6: 75%
|  | Kara ? |  |  |  |  | S1: 100%; S2: 100%; S3: 25%; S4: 25%; S5: 75%; S6: 75%
|  | Unidentiied QA |  |  |  |  | S1: 100%; S2: 100%
|  | Unidentiied QA |  |  |  |  | S1: 100%; S2: 100%
|  | Unidentiied QA |  |  |  |  | S1: 100%; S2: 100%
[5 empty] | Site Activation Enhancements¦ Activation Reports - Pending Action Report | S
000 | Dev | Wyatt | 1 |  |  |  | S1: 25%
| Dev | Peter / Jay | 1 |  |  |  | S1: 50%
| Dev | Luke | 1 |  |  |  | S1: 75%
| Dev | Nate | 1 |  |  |  | S1: 50%
| QA | Irina | 0.5 |  |  |  | S1: 100%
| QA | Andrey | 0.5 |  |  |  | S1: 100%
| QA | Joseph | 1 |  |  |  | S1: 100%
| QA | Sam | 1 |  |  |  | S1: 100%
|  |  | Discuss Time Box |  | Site Activation Enhancements¦Country/Study WF¦ Concept, Discovery and Ideation | S
000 | Dev | Wyatt | 1
| Dev | Peter / Jay | 1 |  |  |  | S3: 100%; S4: 100%
| Dev | Luke | 1 |  |  |  | S3: 100%; S4: 100%
| Dev | Nate | 1
| QA | Irina | 0.5
| QA | Andrey | 0.5 |  |  |  | S3: 100%; S4: 75%
| QA | Joseph | 1
| QA | Sam | 1 |  |  |  | S3: 100%; S4: 75%
|  |  |  | Dependency: UX | Site Activation Enhancements¦Country/Study WF¦ Country Level Activation | XL
000 | Dev | Wyatt | 1 |  |  |  | S4: 50%; S5: 100%; S6: 100%
| Dev | Peter / Jay | 1 |  |  |  | S5: 100%; S6: 100%
| Dev | Luke | 1
| Dev | Nate | 1
| QA | Irina | 0.5 |  |  |  | S4: 50%; S5: 100%; S6: 100%
| QA | Andrey | 0.5
| QA | Joseph | 1
| QA | Sam | 1 |  |  |  | S4: 25%; S5: 100%; S6: 100%
[5 empty] | Site Activation Enhancements¦Country/Study WF¦ Study Level Activation | XL
000 | Dev | Wyatt | 1
| Dev | Peter / Jay | 1
| Dev | Luke | 1 |  |  |  | S5: 100%; S6: 100%
| Dev | Nate | 1 |  |  |  | S4: 50%; S5: 100%; S6: 100%
| QA | Irina | 0.5
| QA | Andrey | 0.5 |  |  |  | S4: 25%; S5: 100%; S6: 100%
| QA | Joseph | 1 |  |  |  | S4: 25%; S5: 100%; S6: 100%
| QA | Sam | 1
[5 empty] | Performance and Scalability ¦ Site Activation ¦ Workflow- Tech Debt | M
000 | Dev | Wyatt | 1 |  |  |  | S1: 50%
| Dev | Peter / Jay | 1 |  |  |  | S2: 75%
| Dev | Luke | 1 |  |  |  | S1: 50%
| Dev | Nate | 1 |  |  |  | S2: 50%
| QA | Irina | 0.5
| QA | Andrey | 0.5
| QA | Joseph | 1 |  |  |  | S1: 50%; S2: 25%
| QA | Sam | 1
[5 empty] | Performance and Scalability ¦ Site Activation ¦ Checklist - Tech Debt | M
000 | Dev | Wyatt | 1 |  |  |  | S2: 50%
| Dev | Peter / Jay | 1 |  |  |  | S1: 50%
| Dev | Luke | 1
| Dev | Nate | 1 |  |  |  | S1: 25%; S2: 50%
| QA | Irina | 0.5
| QA | Andrey | 0.5
| QA | Joseph | 1 |  |  |  | S1: 50%; S2: 25%
| QA | Sam | 1
[5 empty] | Site Activation Enhancements¦Cross Trial ¦ Concept | N/A
000 | Dev | Wyatt | 1
| Dev | Peter / Jay | 1
| Dev | Luke | 1
| Dev | Nate | 1
| QA | Irina | 0.5
| QA | Andrey | 0.5
| QA | Joseph | 1
| QA | Sam | 1
[5 empty] | Site Activation Enhancements¦Additional Features¦ Concept | N/A
000 | Dev | Wyatt | 1
| Dev | Peter / Jay | 1
| Dev | Luke | 1
| Dev | Nate | 1
| QA | Irina | 0.5
| QA | Andrey | 0.5
| QA | Joseph | 1
| QA | Sam | 1
[5 empty] | Persistory Planning | XS
000 | Dev | Wyatt | 1 |  |  |  | S3: 100%; S4: 50%
| Dev | Peter / Jay | 1
| Dev | Luke | 1
| Dev | Nate | 1 |  |  |  | S3: 100%; S4: 50%
| QA | Irina | 0.5 |  |  |  | S3: 100%; S4: 50%
| QA | Andrey | 0.5
| QA | Joseph | 1 |  |  |  | S3: 100%; S4: 50%
| QA | Sam | 1
Train Crusher on Ember
000 | Dev | Wyatt | 1
| Dev | Peter / Jay | 1
| Dev | Luke | 1 |  |  |  | S2: 50%
| Dev | Nate | 1
| QA | Irina | 0.5
| QA | Andrey | 0.5
| QA | Joseph | 1
| QA | Sam | 1
Sum Total
| Dev | Wyatt | 1 |  |  |  | S1: 75%; S2: 50%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
| Dev | Peter / Jay | 1 |  |  |  | S1: 100%; S2: 75%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
| Dev | Luke | 1 |  |  |  | S1: 125%; S2: 50%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
| Dev | Nate | 1 |  |  |  | S1: 75%; S2: 100%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
| QA | Irina | 0.5 |  |  |  | S1: 100%; S2: 0%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
| QA | Andrey | 0.5 |  |  |  | S1: 100%; S2: 0%; S3: 100%; S4: 100%; S5: 100%; S6: 100%
| QA | Joseph | 1 |  |  |  | S1: 200%; S2: 50%; S3: 100%; S4: 75%; S5: 100%; S6: 100%
| QA | Sam | 1 |  |  |  | S1: 100%; S2: 0%; S3: 100%; S4: 100%; S5: 100%; S6: 100%

## Boston Q4 2018 Plan (hidden)
ID | Team | Initiative | Q4 Initiative Description | Initiative Prior (C, H, M, L) | Initiative Rank | Initiative Category | Phase | Workstream | Client Impact | Unique QB | Rank Order | Target Delivery Month | Customer Impact Month | Quarterly Business Objectives | Epic Summary | Epic Shortname | Epic Description | Epic Priority (C, H, M, L) | Epic Ranking | Story Summary | Delivery Target | T-Shirt Size | Story Points | Scrum Team | In Scope or Out of Scope | Product Lead
X | L | Investigator Registry NR | IR for SIP 3.1 [Colin M] | C | 1 | External Commitment | Implementation | P-API | Transcelerate | X | 1 | October | October | Colin M | Colin M |  | Colin M | C
X | B | eTMF API Delivery V1 | Enable DD assets to be transferred to the sponsor system in systemic industry standards to address compliance requirements and current inefficiencies to address the short comings. Data APIs to be consumed by PS Team to enable Asset transfer (Email, BlogPost, Training Reports) to Janssen and Doc Library to Novartis | C | 2 | External Commitment | Implementation | API | Janssen |  |  | October | January | eTMF enabled APIs for Training Reports, Blog Posts andEmail Blasts so that enterprise customer have an automated process to access crucial artifacts within their etmf to enable efficiency and accuracy | Extractor Jobs to generate artifacts for 3 modules | Extractor Jobs | As a PS implemetation Manager, I would like to get Extractor Jobs to generate artifacts for 3 key modules so that I can file important trial information in the client's TMF. | C |  |  |  | S | Ops deployed sync up on S3 buckets | EPL & 000
| B | eTMF API Delivery V1 | Enable DD assets to be transferred to the sponsor system in systemic industry standards to address compliance requirements and current inefficiencies to address the short comings.Data APIs to be consumed by PS Team to enable Asset transfer (Email, BlogPost, Training Reports) to Janssen and Doc Library to Novartis | C | 2 | External Commitment | Implementation | API | Janssen | X | 2 | October | December | eTMF enabled APIs for Training Reports, Blog Posts andEmail Blasts so that enterprise customer have an automated process to access crucial artifacts within their etmf to enable efficiency and accuracy | Data APIs to accept request for asset extractions | Data APIs | As a PS implemetation Manager, I would like to have Data APIs to accept requests for asset extractions so that I can easily pull data out of the Platform. | C |  | Subject of an email Body of an email Push weekly email to XXX Reconcilation email | 2018-12-18 | S | EPL and PS Int collab | EPL & 000 | In Scope
| B | eTMF API Delivery V1 | Enable DD assets to be transferred to the sponsor system in systemic industry standards to address compliance requirements and current inefficiencies to address the short comings. V1 will address Data APIs to be consumed by PS Team to enable Asset transfer (Email, BlogPost, Training Reports) to Janssen and Doc Library to Novartis | C | 2 | External Commitment | Implementation | API | Vertex/ Novartis | X | 3 | October | January | eTMF enabled APIs for Document Library so that metadata is standardized to be used as common API service from receiving party | Metadata is standardized to be used as common API service from receiving party | Standardized Metadata | As a PS implemetation Manager, I would like to have standard DIA formed metadata to be used as common API service from receiving party so that I can match files to the appropriate location in the client's TMF. | H |  |  |  | S |  | EPL & 000
| B | Site Activation Reporting | Providing better site activation reporting would allow sponsors to have increased visibility into their trial’s activation process. This would be improved with improved cycle time, country roll up, detailed site, cross trial and dashboard reporting. | C | 5 | Product Enhancement | Implementation | Site Activation | Vertex/ Novartis | X | 4 | October | December | Implement URS defined most Critical Requirements for Client Commitment to address: 1. Group document states to consolidate information from all sites and countries 2. View Site Activation document status for all sites 3. View cycle times for Site Activation documents 4. Allow Sponsors/CROs to determine which countries, CROs, sites, or business processes are most or least efficient at site activation | Document Grouping by Pending Actors | Doc Grouping by Actors | As a study manager I need the ability to group document states by Pending Actor in order to consolidate information from all sites and countries. |  |  | Spike: Investigate workflow tech debt that will be problems/blockers to further workflow changes. Update Workflow template to include new attribute to designate the Workflow as supporting Pending Actor grouping Update Workflow states to include a Pending Actor selector with the included options. |  | M | Get some input from Slamina on workflow | 000
| B | Versioning and Equivalence | Support the ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 5 | December | March | Ability to upload versioned training content to the sponsor catalog to replace existing trainings. | Allow sponsor to version control training content and upload any type of content and link it to a previous version |  | As a training catalog user I need to upload new versions of trainings and link them to previous versions to better manage training content and end user assignment. | [6 empty] | slamina
| B | Versioning and Equivalence | Support the ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 6 | December | March | Ability to enforce whether an upload of a new version of an assigned cross-trial training should force end users with an existing assignment to retake the training with the new content. | Allow for both retake required and not required after versioning |  | As a training catalog user I need to be able to reassign a new training version to all recipients of the previous version so that end users remain qualified after major changes to relevant traiing content. | [6 empty] | slamina
| B | Versioning and Equivalence | Support the ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 7 | December | March | Ability to release assignments of a new version of an assigned cross trial training to subgroups of countries on a trial via staggered decisions. | Support country-specific versions for trainings |  | As a training catalog user I need to stagger assignment of a new training version to relevant countries so that I can keep end users qualified for trial participation while respecting country regulatory approvals. | [6 empty] | slamina
| B | Versioning and Equivalence | Support the ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 8 | December | March | Support version control traceability in reporting by amending all training reports to show which version of a training a trainee completed. | Reporting must contain information about the version completed |  | As a site manager I need for training completion reports that will be filed in vTMF to specify the verison of a training that a trainee completed so that my trial master file accurately reflects the state of training completion for my site users. | [6 empty] | slamina
| B | Versioning and Equivalence | Support the ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 8 | December | March | Support versioning of quiz content to maintain parallel updates of content and evaluations when training materials are versioned. | Allow for quiz content to be versioned when training content is updated. |  | As a training catalog user I need to version training quizzes so that I can update training evaluations in parallel with updating training content. | [6 empty] | slamina
| B | Versioning and Equivalence | Support the ability for sponsor users to manage equivalent training credit from a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 10 | December | March | Enable sponsor to manage language equivalence for cross-trial training content. | Allow sponsor to equate completion credit for two different cross-trial trainings. |  | As a training catalog user I need to be able to set the completion of two or more cross-trial trainings as being equivalent to each other so that different translations of trainings can easily be managed. | [6 empty] | slamina
| B | Versioning and Equivalence | Support the ability for sponsor users to manage equivalent training credit from a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 11 | December | March | Enable sponsor to manage relationship between trial-specific branding and general training content templates. | Support trial-specific adaptations of content through equivalence |  | USE CASE PENDING VALIDATION | [6 empty] | slamina
| B | Versioning and Equivalence | Support the ability for sponsor users to manage equivalent training credit from a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 12 | December | March | Able to manage an equivalence relationship while versioning involved content. Q:Are there equivalence relationships that are not 1 to 1? | Manage an equivalence relationship while versioning involved content. Q:Are there equivalence relationships that are not 1 to 1? |  | USE CASE PENDING VALIDATION | [6 empty] | slamina
| B | Versioning and Equivalence | Support the ability for sponsor users to manage equivalent training credit from a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | H | 3 | External Commitment | Implementation | LMS | Janssen | X | 12 | December | March | Enable catalog users to manage protocol amendment trainings. | Handle parallel assignment of versioned, whole trainings and delta protocol trainings as appropriate for approved sites. |  | USE CASE PENDING VALIDATION | [6 empty] | slamina
X | B | Versioning and Equivalence | Support the ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | C | 3 | External Commitment | Discovery | LMS | Janssen | X | 19 | October | October | Complete Discovery phase to enable an ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | Complete discovery phase to finalize concept phase of Versioning and Equivalence |  | As a Product Manager, I want to know the strategy to implement versioning and equivalence within DD Spark System so that I am aware of its impact on context of end to end body of work that needs to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  |  |  |  | L |  | slamina
|  | CrossTrial LMS 2.0 Support | [19 empty] | XS
| B | CrossTrial LMS (2.1) | 2.1 version is a follow up release to additionally support the 2.0 release aka MVP release in September to address missing URS and Must Have enhancements | M | 23 | External Commitment | Implementation | LMS | Janssen | X | 13 | November | March | Enable catalog users to export operationally useful information to be shared with stakeholders that do not have catalog access. | Allow catalog users to export training catalog content and catalog quiz content reports. | Export training catalog reports | As a training catalog user I need to be able to export reports providing information on the configuration of catalog content so that I can kep stakeholders without access to the catalog informed of its current state. | L |  | reports only formats: xls, xlsx, pdf no saved report/ report request page |  | S |  | slamina
| B | CrossTrial LMS (2.1) | 2.1 version is a follow up release to additionally support the 2.0 release aka MVP release in September to address missing URS and Must Have enhancements | M | 23 | External Commitment | Implementation | LMS | Janssen | X | 13 | November | March | Enable sponsor users to manage platform training configuration. | Allow sponsor users to access training configuration and other pages that control training setup within platform (create and edit training modules, create and edit training notifications, create and edit alternate training methods) | Enable sponsor management of platform training | As a training administrator I need to be able to create and edit the configuration of training content within the Spark platform so that I can manage assignment and maintenance of trial training assignment without needing support from PS. | H |  | -define permissions per page -include all training admin permissions plus additions |  | S |  | slamina
| B | CrossTrial LMS (2.1) | 2.1 version is a follow up release to additionally support the 2.0 release aka MVP release in September to address missing URS and Must Have enhancements | M | 23 | Product Enhancement | Implementation | LMS | Janssen | X | 14 | November | March | Address the delayed usability enhancements (inconsistent styling on the training index view, improved styling of the quizzes, improvement of the error handling and messaging for the sync processes). | Update styling throughout training catalog according to UX priority punchlist. | Update training catalog styling | As product I want consistent styling throughout the training catalog and consistent error messaging throughout the user flow so that a predictable and useful experience is supported for LMS users. | M |  |  |  | XS |  | slamina
| B | CrossTrial LMS (2.1) | 2.1 version is a follow up release to additionally support the 2.0 release aka MVP release in September to address missing URS and Must Have enhancements | M | 23 | Product Enhancement | Implementation | LMS | Janssen | X | 14 | November | March | Enable sponsor users to disable and archive trainings to impriove end-of-life content management. | Allow catalog users to archive and disable training content to influence status of trainings assigned to trials and end users. | Retire trainings via catalog | As a catalog user I need to be able to archive cross-trial training content so that it can no longer be sent to trials or assigned to end users in order to retire training content that is no longer in use. | H |  |  |  | L |  | slamina
| B | CrossTrial LMS (2.1) | [11 empty] | Allow users to upload large video files successfully | Multi part upload of large video files | Multi part file upload |  | L |  |  |  | M |  | slamina
| B | CrossTrial LMS (2.1) | [11 empty] | Rationalize permissioning and reduce burden on PS for managing users of the catalog | Internal permissioning tech debt, keycloak improvements | Internal perm. tech debt |  | H |  | Scripting of keycloak clients in admin API Admin utilities for managing group membership from training catalog |  | L |  | slamina
| B | CrossTrial LMS (2.1) | [11 empty] | Allow users to remove catalogs | Improve catalog management | Improve catalog management |  | H |  | Port catalog setup to catalog location Delete a catalog |  | M |  | slamina
| B | CrossTrial LMS (2.1) | [11 empty] | Meet Quality Auditing requirements | Auditing of training catalog functionality | Auditing catalog |  | C |  | Crusher responsibility for handling microservice integration for ATv3 |  | M |  | slamina
| B | CrossTrial LMS (2.1) | [11 empty] | Meet Security requirements | Virus scan of catalog videos | Virus scan of catalog videos |  | Talk to Jeff Liss |  |  |  | L |  | slamina
| B | CrossTrial LMS (2.1) | [11 empty] | Allow other teams to build using Ember in a straightforward manner | Separate tenant zero javascript from tenant pages | Architecture Hardening and Training |  | H |  |  |  | L |  | slamina
| B | CrossTrial LMS (2.1) | 2.1 version is a follow up release to additionally support the 2.0 release aka MVP release in September to address missing URS and Must Have enhancements | M | 23 | Product Enhancement | Implementation | LMS | Janssen | X | 14 | November | March | Address delayed hardening and technical debt deferred from LMS Release 2.0 | Address urgent tech debt for cross-trial LMS functionality. |  | As product I want to address ugent technical debt for the cross-trial training catalog functionality so that I can provide a scalable and error-resistant product for the customer (PENDING BRETT/ TEAM INPUT) |  |  |  |  | N/A |  | slamina
X | B | Site Activation Reporting | Providing better site activation reporting would allow sponsors to have increased visibility into their trial’s activation process. This would be improved with improved cycle time, country roll up, detailed site, cross trial and dashboard reporting. | C | 5 | Product Enhancement | Discovery | Site Activation | Vertex/ Novartis | X | 21 | October | October | Complete Discovery Phase (evaluate and priority/value of the project) associated withSite Activation Reporting | Complete Discovery Phase (evaluate and priority/value of the project) associated with Site Activation Reporting | Discovery Phase | As a Product Manager, I want to carve out Site Activation Reporting Implementation in details to inform the granular implementation within DD Spark System so that I am aware of the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A |  |  |  |  | XS |  | 000
|  | Site Activation Reporting | [11 empty] | Implement URS defined most Critical Requirements for Client Commitment to address: 1. Group document states to consolidate information from all sites and countries 2. View Site Activation document status for all sites 3. View cycle times for Site Activation documents 4. Allow Sponsors/CROs to determine which countries, CROs, sites, or business processes are most or least efficient at site activation | View cumulative cycle times for Site Activation documents with aggregate totals of Document Status. | View cumulative cycle times |  |  |  | New Report to display cycle time history of each document. |  | L |  | 000
| B | Audit Trail v2 | AT V2 initiative addresses the DD Spark's performance/compliance to acheive access to historical and future audit trail data preserved in compliance with 21 CFR part 11 while improving perfromance for future/ anticipated growth of trials | H | 11 | Platform Performance | Implementation | Scalability | All | X | 16 | October | NA | Support 2019 scalability by removing the massive audit trail load in the production db (40% of the db). | Use microservice rather than platform db to display and view audit trail | Microservice for display | As a network administrator, I would like to use microservice rather than platform db to display and view audit trail so that I can access data with faster performance. | H |  |  |  | L | Ops dep on deployment of mongo/kinesis in jenkins and prod QA will require finishing initial testing and then full regression for platform | Crusher
X | B | Delegation Log v2 | Improve on Delegation of Authority Log v1, adding ability to require PI approval, course status, improved email notifications. The result of the implementation should be as follows: 1) At a Trial-level, delegation log tasks can be created and mapped to courses 2) At a Site-level, users can be assigned to tasks, and have trainings automatically assigned. | L | 32 | External Commitment | Discovery | LMS | Janssen | X | 32 | L - December | December | Inform problem associated with delgation log with clear problem statement and details on project scope via detailed discovery to inform the following: 1) At a Trial-level, delegation log tasks can be created and mapped to courses 2) At a Site-level, users can be assigned to tasks, and have trainings automatically assigned. problem deeply and clarify project scope | Complete Discovery Phase (Understand the problem deeply and clarify project scope) associated with Delegation Log V2 Implementation |  | Address Discovery work to address the following: 1. Ability to require PI approval of suggested user-task assignments per site, with training assignment contingent on approval and timestamps on approvals 2. Allow site admins to Assign Tasks to Users with E-signature for PI approval 3. Facilitate flow of updates between study coordinator and PI 4. Improved email notifications - delayed or immediate, consolidated 5. Show Site staff progress on Course and task in UI 6. Calculate qualification date of a task for a user, based on training completion dates 7. Copy duties to another trial 8. Smart handling of end-dating of tasks/trainings |  |  |  |  | M |  | slamina
X | B | eTMF API Delivery V2 | Enable DD assets to be transferred to the sponsor system in systemic industry standards to address compliance requirements and current inefficiencies to address the short comings. Data APIs to be consumed by external sponsors to enable Asset transfer from DD Spark without PS Engagement | C | 6 | External Commitment | Ideation | API | IQVIA/Vertex/ Novartis | X | 40 | December | December | Ideation Phase completion to inform Data APIs to be consumed by external sponsors to enable Asset transfer from DD Spark without PS Engagement | Ideation Phase completion to inform Data APIs to be consumed by external sponsors to enable Asset transfer from DD Spark without PS Engagement | Data API Ideation Phase | Ideation Phase completion to inform Data APIs to be consumed by external sponsors to enable Asset transfer from DD Spark without PS Engagement. Following deliverables will follow: 1. List of epics 2. Refined "epic level" estimates and risks 3. Storymaps or N/A 4. Prototype and/or high level arch direction or N/A 5. Experience design or N/A |  |  |  |  | S |  | EPL
| B | Audit Trail v3 | AT V3 initiative continues to address DD Spark's performance/compliance by addressing data search and preservation | M | 27 | Platform Performance | Implementation | Scalability | All | X | 18 | November | NA | To provide a better user experience when searching audit trail records remove audit trail entirely from platform. | Micro service Supports Direct Logging of audit trail records. | Microservice: Direct Logging | Implementation | [6 empty] | Crusher
X | L | Site SSO (Core) | Implement the logic and user flows related to site-based users of Spark, accounting for multiple sponsor IDPs. [Mike B- Please try to address what happens if we don't do it question?] . Not doing this work would mean we will not be ready to deliver on enterprise customer commitments in Q1/19. | C | 4 | External Commitment | Ideation | SSO | Janssen/Novartis | x |  | December | January | To implement the logic and user flows related to site-based users of Spark, accounting for multiple sponsor IDPs
| B | Site Activation Reporting | Providing better site activation reporting would allow sponsors to have increased visibility into their trial’s activation process. This would be improved with improved cycle time, country roll up, detailed site, cross trial and dashboard reporting. | C | 5 | Product Enhancement | Implementation | Site Activation | Vertex/ Novartis |  |  | October | December | Implement URS defined most Critical Requirements for Client Commitment to address: 1. Group document states to consolidate information from all sites and countries 2. View Site Activation document status for all sites 3. View cycle times for Site Activation documents 4. Allow Sponsors/CROs to determine which countries, CROs, sites, or business processes are most or least efficient at site activation | View Site Activation document status for all sites | View Doc Status | As a study manager I need the ability to view Site Activation document status for all sites with unified Pending Actor categories in order to understand start-up progress and common pain points. |  |  | Update Site Activation Detailed Report to include Pending Actor status for each site document. |  | XS |  | 000
X | B | Cross Trial Reporting | Provide cross trial reporting enables our sponsors and the users of the system with visibity that informs the trail management decisions and actions enabling effectiveness of the overall DrugDev Product. | C | 7 | Product Enhancement | Concept | Clinical Technology | NA | x | 25 | November | November | Ability to provide the cross trial reporting enables our sponsors and the users of the system with visibity that informs the trail management decisions and actions enabling effectiveness of the overall DrugDev Product. Complete concept to inform Cross Trial Reporting and distinct business value proposition | Complete the Concept Phase on Cross Trial Reporting |  | As a product manager, I would like to evaluate priority and value of proposed cross trial reporting feature in DrugDev Spark to address: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups 6. Business decision to schedule or put on hold |  |  |  |  | S | Cross-team dependency on plan for reporting requirements from across modules. London/Crusher | 000
| B | Scalability and Performance | Determine if 2019 growth with drive platform performance beyond a breaking point. | M |  | Platform Performance |  | Scalability | All | X |  |  |  | Support 2019 scalability by highlighting protential problems.
X | B | eSig | Enabling clients to use eSignature in Training Delegation Log and Site Activation is critical to success to ensure the compliance requirements are met and to reduce errors / inefficiencies with end to end process to complete the training workflow and site activation workflow | C | 9 | External Commitment | Concept | Site Activation and LMS | Janssen, Vertex | X | 21 | October | October | eSig as part of the initiative in the DrugDev System needs to be implemented, this objective will fullfill deilverables associated with the Concept of the eSig Implementation to confirm the following: 1. Confirm licencing vs. drugdev developed solution 2. If licencing, confirm API data contracts 3. User experience to invoke and complete esignature action 4. Confirm exptectation for vTMF esignature needs 5. End to End Architectural/Desgin brief with eSingature as a feature with DrugDev Spark Product | Complete Concept Phase (evaluate and priority/value of the project) associated with eSig Implementation |  | As a Product Manager, I want to know the strategy to eSig Implemntation within DD Spark System so that I am aware of its impact on context of end to end body of work that needs to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold | H |  |  |  | Done |  | slamina
| B | eTMF API Delivery V2 | Enable DD assets to be transferred to the sponsor system in systemic industry standards to address compliance requirements and current inefficiencies to address the short comings. Data APIs to be consumed by external sponsors to enable Asset transfer from DD Spark without PS Engagement | C | 6 | External Commitment | Discovery | API | IQVIA/Vertex/ Novartis | X | 24 | November | November | Discovery Phase completion to inform Data APIs to be consumed by external sponsors to enable Asset transfer from DD Spark without PS Engagement | Discovery Phase completion to inform Data APIs to be consumed by external sponsors to enable Asset transfer from DD Spark without PS Engagement | Data API Discovery Phase | Discovery Phase completion to inform Data APIs to be consumed by external sponsors to enable Asset transfer from DD Spark without PS Engagement. Following deliverables will follow: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. Confirm project(s) scope/goals/success criteria 6. Revise project level estimates and risks 7. Design brief or N/A 8. Architecture brief or N/A |  |  |  |  | XS |  | EPL
| B | Versioning and Equivalence | Support the ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | C | 3 | External Commitment | Ideation | LMS | Janssen | X | 33 | October | NA | Complete Ideation phase to enable an ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | Complete ideation phase to finalize concept phase of Versioning and Equivalence |  | As a Product Manager, I want to complete an analysis in order to confirm design and architecture direction and refine estimates to inform versioning and equivalence implementation within DD Spark System so that I am able to work on its design to inform the story grooming and estimates for the product feature. Address the following: 1. List of epics 2. Refined "epic level" estimates and risks 3. Storymaps or N/A 4. Prototype and/or high level arch direction or N/A 5. Experience design or N/A | [6 empty] | slamina
X | B | Search | Impove search functionality comparable to the industry standards while ensuring the search, find and list use cases are managed while considering performance and scalability | C | 10 | Product Enhancement | Ideation | Trial Management | All | X | 36 | December | NA | Search Engine as part of the initiative in the DrugDev System needs to be implemented, this objective will fullfill deilverables associated with the Ideation of the Search Engine Implementation | Complete Ideation Phase (Complete initial analysis in order to confirm design and architecture direction and refine estimates ) associated with associated with Search Engine Implementation | Ideation Phase | As a Product Manager, I want to complete analysis in order to confirm design and architecture direction and refine estimates to inform Search Engine Implementation within DD Spark System so that I am able to work on its design to inform the story grooming and estimates for the product feature. Address the following: 1. List of epics 2. Refined "epic level" estimates and risks 3. Storymaps or N/A 4. Prototype and/or high level arch direction or N/A 5. Experience design or N/A |  |  |  |  | XS |  | EPL
| B | Search | Impove search functionality comparable to the industry standards while ensuring the search, find and list use cases are managed while considering performance and scalability | C | 10 | Product Enhancement | Concept | Trial Management | All | X | 34 | October | NA | Search Engine as part of the initiative in the DrugDev System needs to be implemented, this objective will fullfill deilverables associated with the Concept of Search Implementation to confirm the following: 1. Confirm licencing vs. drugdev developed solution 2. User experience to invoke and complete search action 3. End to End Architectural/Desgin brief with Search as a feature with DrugDev Spark Product | Complete Concept Phase (evaluate and priority/value of the project) associated with eSig Implementation | Concept Phase | As a Product Manager, I want to know the search engine strategy along with user experience within DD Spark System so that I am aware of its impact on context of end to end body of work that needs to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  |  |  |  | XS |  | EPL
| B | Site Activation Reporting | Providing better site activation reporting would allow sponsors to have increased visibility into their trial’s activation process. This would be improved with improved cycle time, country roll up, detailed site, cross trial and dashboard reporting. | C | 5 | Product Enhancement | Implementation | Site Activation | Vertex/ Novartis |  |  | October | December | Implement URS defined most Critical Requirements for Client Commitment to address: 1. Group document states to consolidate information from all sites and countries 2. View Site Activation document status for all sites 3. View cycle times for Site Activation documents 4. Allow Sponsors/CROs to determine which countries, CROs, sites, or business processes are most or least efficient at site activation | View current Status cycle time and cycle time since initial action for Site Activation documents | View status cycle time | As a study manager I need the ability to view cycle times for Site Activation documents in order to report performance of Study Start Up and calculate ROI. |  |  | Investigate arch/new data model to collect and store this data. Update Site Activation Detailed Report to include days in current Pending Actor status and total days since initial document action. |  | S |  | 000
X | L | Front End User Management Tools | All trial users of the enterprise systems are managed via CTMS (Source of Truth) via integration enable user access and user management via a central system | C | 8 | External Commitment | Discovery | CTMS | Janssen | x |  | September | September | Complete discovery to inform the Front End User Mangement Scope so that Clients (Janssen) to address issues on user reconcilation/ migration as needed and enable single sourced user managment includes creation of new users and deactivate existing users | Confirm project(s) scope/goals/success criteria Revise project level estimates and risks Design brief or N/A Architecture brief or N/A |  |  | H
| B | Search | Impove search functionality comparable to the industry standards while ensuring the search, find and list use cases are managed while considering performance and scalability | C | 10 | Product Enhancement | Discovery | Trial Management | All | X | 35 | November | NA | Search Engine as part of the initiative in the DrugDev System needs to be implemented, this objective will fullfill deilverables associated with the Discovery of the Search Engine Implementation | Complete Discovery Phase (Complete Concept Phase (evaluate and priority/value of the project) associated with eSig Implementation ) associated with Search Engine Implementation | Discovery Phase | As a Product Manager, I want to carve out Search Engine Implementation in details to inform the granular implementation within DD Spark System so that I am aware of the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A |  |  |  |  | XS |  | EPL
X | B | Scalability and Performance | AT V2 initiative addresses the DD Spark's performance/compliance to acheive access to historical and future audit trail data preserved in compliance with 21 CFR part 11 while improving perfromance for future/ anticipated growth of trials | H | 11 | Platform Performance | Implementation | Scalability | All | X | 15 | October | NA | Support 2019 scalability by removing the massive audit trail load in the production db (40% of the db). | Determine value and scope to delete audit trail data from production | Value & Scope | As an operations manager, I would like to be able to delete audit trail data from production so that I can reduce the size of the database to improve performance and maintance of production infrastructure. | H |  |  |  | XS |  | Crusher
| B | Scalability and Performance | Address scalability short-term and long term goals to prepare for high trial volume while addressing the current and known future issues | H | 13 | Platform Performance | Concept | Scalability | NA | X | 37 | December | NA | Email Blast Scalability: M To ensure that we can scale email blasts to support 2019 trial capacity, and possibly allow end-users to send email blasts. | Address issues with Email Blast Scalability | Email Blast Issues | As a product manager, I would like to investigate and evaluate current and projected email blast volume based on new 2019 trials so that I can ensure our platform and email infrastructure will be capable of dealing with expected growth. | H |  |  |  | XS to finish plan S to execute plan and get numbers |  | EPL
| B | Scalability and Performance | Address scalability short-term and long term goals to prepare for high trial volume while addressing the current and known future issues | H | 13 | Platform Performance | Concept | Scalability | NA | X | 38 | December | NA | RDS Replica in Production: Provide functionality like custom reports, sync jobs, or extractions while preventing them from taking the system down. | Address issues with RDS Replica in Production and determine work needed | RDS Replica Issues | As a product manager, I would like to address segment long-running queries and reports so they are using a read-only db so that I can deliver user-features that aren't effecting production performance. | M |  | Build and manage RDS read replicas Reliable replica that new features could leverage |  | XS |  | Crusher
| B | Scalability and Performance | Address scalability short-term and long term goals to prepare for high trial volume while addressing the current and known future issues | H | 13 | Scalability | Concept | eTMF | NA | X | 39 | December | NA | Move to Sidekick Event system: M To meet 2019 trial capacity and eTMF data extraction initiative, improve capacity to handle background tasks | Move to Sidekick Event system | Sidekick Event Sys | As a product manager, I would like to have the team prototype and evaluate, with eTMF APIs as a test so that we may decide if we want to use it further for the Gradual rollout in 2019 to replace existing delayed jobs to improve platform performance of operational efficiencies. | M |  |  |  | S |  | EPL
| B | Scalability and Performance | Address scalability short-term and long term goals to prepare for high trial volume while addressing the current and known future issues | H | 13 | Platform Performance | Concept | Scalability | NA | X | 40 | December | NA | Search Patches: M To allow users to search for new documents without a long lag and allows the business to delay the larger Search project. | Search Patches | Search Patches | As a product manager, I would like the team to improve search index (currently takes at least 13 hours) and ix 100% CPU utilization for search engine (currently requires reboot) so that reduce operational cost and deliver improved end user search functionality. | M |  | Fix document indexer to reduce processing time. |  | XS |  | EPL
| B | Scalability and Performance | Address scalability short-term and long term goals to prepare for high trial volume while addressing the current and known future issues | H | 13 | Platform Performance | Concept | Scalability | NA | X | 41 | December | NA | Queue integration chron jobs: M To meet demands of uploading data by integrations in 2019 - which are currently scheduled and we are running out of time slots. | Queue integration cron jobs | Queue Cron Jobs | As a operations manager, I would like to have a better queue/job system for running background integration jobs in a sequential manner and add more job servers as needed so that I can reduce the burden on application servers and improve infrastructure efficiencies. | M |  |  |  | S |  | EPL
| B | Scalability and Performance | Address scalability short-term and long term goals to prepare for high trial volume while addressing the current and known future issues | H | 13 | Maintenance | Concept | Maintenance | NA | X | 42 | December | NA | Ongoing Upgrades for Rails, Gems, other software: L To ensure continued SOC2 compliance, ensure we are up to date with security patches on an ongoing basis. | Ongoing Upgrades for Rails, Gems, other software |  | As a product manager, I would like engineering team to perform quarterly evaluation of what needs to be upgraded and risks of not doing so and make release plans for when we will do upgrades and to further inform our testing strategy so that we maintain SOC2 compliance and enable new technologies to be utilized across our codebase. | L | [5 empty] | Q1
X | B | Site Activation Cross Trial | Enable site activation artifacts to be used centrally with multiple trails by setting it up once to reduce inefficiencies and duplication resulting in error | H | 12 | External Commitment | Concept | Site Activation | Novartis/IQVIA | X | 26 | November | November | Complete Concept Phase (evaluate and priority/value of the project) associated with Site Activation Cross Trial | Complete Concept Phase (evaluate and priority/value of the project) associated with Site Activation Cross Trial Implementation | Con | As a Product Manager, I want to know the strategy to implement Site Activation Cross Trial within DD Spark System so that I am aware of its impact on context of end to end body of work that needs to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  |  |  |  | S | Consider the ability to leverage Golden Number from Site/Users could include depenency on London and Crusher | 000
| B | Site Activation Cross Trial | Enable site activation artifacts to be used centrally with multiple trails by setting it up once to reduce inefficiencies and duplication resulting in error | H | 12 | External Commitment | Discovery | Site Activation | Novartis/IQVIA | X | 27 | November | November | Complete Discovery Phase (evaluate and priority/value of the project) associated with Site Activation Cross Trial | Complete Discovery Phase (evaluate and priority/value of the project) associated with Site Activation Cross Trial | Disc | As a Product Manager, I want to carve out Site Activation Cross Trial Implementation in details to inform the granular implementation within DD Spark System so that I am aware of the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A |  |  |  |  | M |  | 000
| B | Scalability and Performance | Address scalability short-term and long term goals to prepare for high trial volume while addressing the current and known future issues | H | 13 | Platform Performance | Concept | Scalability | NA | X | 43 | December | NA | Move to RDS Arora: L To meet 2019 trial capacity, improve database performance through an upgrade to arora. | Move to RDS Arora |  | As a product manger, I would like to Investigate what performance gains AWS Arora would give us and what testing/Devops effort would be required (mainly Devops/QA) so that we can plan for it's inclusion on the release schedule. | L | [5 empty] | Ops
| B | Versioning and Equivalence | Support the ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | C | 3 | External Commitment | Discovery | LMS | Janssen | X | 20 | October | October | Complete discovery phase work to enable an ability for sponsor users to version control training content in a central repository while seamlessly managing end user assignment and cross-trial training completion credit. | Complete discovery phase to finalize concept phase of Versioning and Equivalence |  | As a Product Manager, I want to carve out versioning and equivalence implementation in details to inform the granular implementation within DD Spark System so that I am aware of the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A | [6 empty] | slamina
X | B | Scalability and Performance | Address scalability short-term and long term goals to prepare for high trial volume while addressing the current and known future issues | H | 13 | Platform Performance | Implementation | Scalability | NA | X | 17 | ? | NA | Long Running Queries: H To support onboarding new trials from Janssen, IQVIA, etc, need to ensure that the system does not crash from long running queries. | Address issues with Long Running Queries | Long-running queries | As an operations manager, I would like to address the queries that takes 5 or more seconds so that I can improve performance for end users and decrease the likelihood of system degradation. | H |  |  |  | S |  | 000
| B | eSig | Enabling clients to use eSignature in Training Delegation Log and Site Activation is critical to success to ensure the compliance requirements are met and to reduce errors / inefficiencies with end to end process to complete the training workflow and site activation workflow | C | 9 | External Commitment | Discovery | Site Activation and LMS | Janssen, Vertex |  |  | October |  | eSig as part of the initiative in the DrugDev System needs to be implemented, this objective will fullfill deilverables associated with the Discovery of the eSig Implementation | Complete Discovery Phase (Complete Concept Phase (evaluate and priority/value of the project) associated with eSig Implementation ) associated with eSig Implementation |  | As a Product Manager, I want to carve out eSig Implementation in details to inform the granular implementation within DD Spark System so that I am aware of the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A | H |  |  |  | Large for Discovery + Ideation |  | slamina
| B | eSig | Enabling clients to use eSignature in Training Delegation Log and Site Activation is critical to success to ensure the compliance requirements are met and to reduce errors / inefficiencies with end to end process to complete the training workflow and site activation workflow | C | 9 | External Commitment | Ideation | Site Activation and LMS | Janssen, Vertex |  |  | November/ December |  | eSig as part of the initiative in the DrugDev System needs to be implemented, this objective will fullfill deilverables associated with the Ideation of the eSig Implementation | Complete Ideation Phase (Complete initial analysis in order to confirm design and architecture direction and refine estimates ) associated with associated with eSig Implementation |  | As a Product Manager, I want to complete analysis in order to confirm design and architecture direction and refine estimates to inform e-Sign implementation within DD Spark System so that I am able to work on its design to inform the story grooming and estimates for the product feature. Address the following: 1. List of epics 2. Refined "epic level" estimates and risks 3. Storymaps or N/A 4. Prototype and/or high level arch direction or N/A 5. Experience design or N/A | [6 empty] | slamina
X | L | IQVIA CTMS and SSO | Resolve email address mismatch issues between IQVIA's AD, their CTMS feed, Spark and Keycloak | H | 14 | External Commitment | Implementation | SSO/ CTMS | IQVIA | x |  | December | Mike B | To connect Spark/Keycloak to IQVIA's PingFederate environment and define user management processes
x | L | DQS - Indexer Optimisation | Undertake optimisation on the indexer for DQS to improve searching and updating of results | H | 16 | Internal Commitment/Performance | Concept | CTMS/Data Service | IDB/TrC Members | x |  | December | Mike B | Updating people or facilities in a real-time (or overnight T+1) basis as they are added to Data Services. This will include making them searchable by criteria within DQS | [6 empty] | Q4 2018 | H |  |  | In Scope | Kirithika
x | L | Infrastructure - Ubuntu upgrade | Upgrade all servers to latest version of Ubuntu [Colin M] | H | 17 | Internal commitment | Implementation | CTMS/Data Service/IR | IDB/TrC Members | x |  | December | Mike B | Upgrading to latest version of Ubuntu | [6 empty] | Q4 2018 | M |  |  | In Scope | Kirithika
x | L | Profiles - Connect Tech Debt | Front End Technical debt [Colin M.] | H | 18 | Internal commitment | Implementation | CTMS/Data Service/IR | IDB/TrC Members | x |  | December | Mike B | [7 empty] | Q4 2018 | M |  |  | In Scope
X | L | DQS Refactoring/Tech Debt | Colin Mitchell to fill in more information here | H | 19 |  | Concept | DQS | IDB/TrC Members | x |  | November | Mike B
X | B | Clin Tech Navigation | End to end clinical technology navigation and information architecture should be aligned, this project will address the gaps and the report out the results for 2019 user experience initiatives | H | 15 | Product Enhancement | Concept | User Experience | NA | X | 44 | December | NA | Complete concept to inform Clin Tech Navigation with distinct business value proposition and proposed deliverables to meet the business objectives | Complete the Concept Phase of ClinTech Navigation to address holistic experience |  | As a user experience strategist, I would like to evaluate priority and value of proposed uniform clinical technology experience project while addressing : 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups 6. Business decision to schedule or put on hold |  |  |  |  | L |  | slamina
| B | Site Activation Reporting | Providing better site activation reporting would allow sponsors to have increased visibility into their trial’s activation process. This would be improved with improved cycle time, country roll up, detailed site, cross trial and dashboard reporting. | C | 5 | Product Enhancement | Ideation | Site Activation | Vertex/ Novartis | X | 23 | October | October | Complete Ideation Phase (Complete initial analysis in order to confirm design and architecture direction and refine estimates ) associated with Site Activation Reporting | Complete Ideation Phase (Complete initial analysis in order to confirm design and architecture direction and refine estimates ) associated with Site Activation Reporting |  | As a Product Manager, I want to complete analysis in order to confirm design and architecture direction and refine estimates to informSite Activation Reporting implementation within DD Spark System so that I am able to work on its design to inform the story grooming and estimates for the product feature. Address the following: 1. List of epics 2. Refined "epic level" estimates and risks 3. Storymaps or N/A 4. Prototype and/or high level arch direction or N/A 5. Experience design or N/A |  |  |  |  | S | Consider future work on Cross-trial reporting | 000
| L | IR for SIP 3.1 | Complete development and tetsing for new IR endpoints for SIP R3.1 [Colin M.] | H | 20 | External Commitment | Implementation | CTMS/Data Service/IR | IDB/TrC Members | x |  | December | Mike B | Completing development and supporting testing by SIP for Q1 2019 release | IR for SIP R3.1 | PAPI-1086 | This covers all elements for R3.1 release | H |  |  | Q1 2019 | M |  |  | In Scope | Colin
| B | Apollo Design System Adoption | End to end clinical technology navigation and information architecture should be aligned, this project will address the gaps and the report out the results for 2019 user experience initiatives via the Apollo Desgin System Adoption. | H | 20 | Internal commitment | Discovery | User Experience | Internal/ All System Users |  |  | December |  | There is a need to transform the end to end clinical design to adopt a uniform view to manage user experience and information architecture. The Q4 effort will address Strategy/LOE on transformation from Current DD systems to Apollo Design Model considering various modules in the system. | Complete the Discovery Phase for Apollo Design System Adoption |  | As a user experience strategist, I want to understand the end to end LOE based on priority and findings from analysis on tranformation from DD Spark System to Apollo System. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A |  |  |  |  | XL |  | slamina |  | Michelle
x | B | Apollo Design System Adoption | End to end clinical technology navigation and information architecture should be aligned, this project will address the gaps and the report out the results for 2019 user experience initiatives via the Apollo Desgin System Adoption. | H | 20 | Internal commitment | Concept | User Experience | Internal/ All System Users | X | 46 | December | NA | There is a need to transform the end to end clinical design to adopt a uniform view to manage user experience and information architecture. The Q4 effort will address Strategy/LOE on transformation from Current DD systems to Apollo Design Model considering various modules in the system. | Complete the Concept Phase for Apollo Design System Adoption |  | As a user experience strategist, I want to know the strategy to address the transformation of current DD Spark System to Apollo system so that I am aware of the impact on existing experience of the users that can be translated to the implementation LOE. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  |  |  |  | S |  | slamina |  | Michelle
X | B | CrossTrial LMS (2.1) | 2.1 version is a follow up release to additionally support the 2.0 release aka MVP release in September to address missing URS and Must Have enhancements | M | 23 | External Commitment | Implementation | LMS | Janssen | X | 13 | November | March | Enable site managers to manually maintain training assignment and reassignment in cases of required re-training. | Allow site managers to manually reassign latest training content to end users. |  | As a site manager I need to be able to manually reassign the latest version of a an existing cross-trial training assignment to end users at sites that I manage in order to seamlessly manage qualification when re-training is required. | [6 empty] | slamina
X | L | Site SSO (JAN) | Lay the groundwork for implementing Site SSO for Janssen in Q1 [Mike B] | M | 21 | External Commitment | Implementation | SSO | Janssen | x |  | December | Mike B | To connect Spark/Keycloak to Janssen's Exostar ecosystem, and implement on-going user management processes
| L | Front End User Management Tools | All trial users of the enterprise systems are managed via CTMS (Source of Truth) via integration enable user user access and user management via a central system | H | 8 | External Commitment | Ideation | CTMS | Janssen | x | 22 | October | October | Complete ideation to enable eSignature capability on SiteActivation and LMS to adhere to FDA compliance corresponding with the client needs while reducing manual workaround | List of epics Refined "epic level" estimates and risks Storymaps or N/A Prototype and/or high level arch direction or N/A Experience design or N/A
| B | Clin Tech Navigation | End to end clinical technology navigation and information architecture should be aligned, this project will address the gaps and the report out the results for 2019 user experience initiatives | H | 15 | Product Enhancement | Discovery | User Experience | NA | X | 45 | December | NA | Complete discovery to inform Clin Tech Navigation with distinct business value proposition and proposed deliverables to meet the business objectives | Complete the Discovery Phase of ClinTech Navigation to address holistic experience |  | As a user experience strategist, I would like to understand the implications (understand the problem deeply and clarify project scope) of the defination of the uniform clinical technology experience to address the following: 1. Outline of project scope/goals 2. Identify constraints or risks 3. Initial project level estimates 4. UX vision mockups or N/A 5. Business decision to schedule or put on hold |  |  |  |  | XL |  | slamina
X | B | Trial Archive | This project is to implement a new process(es) to archive data related to a closed study to address the current lack of process to systemically archive study data from production database. Simplified process is needed to reduce strain on PS and Ops and improve responsiveness to clients. The implementation should result in secure, validated process to request, action, and execute a full archive of all data related to a tenant and archived data is stored in a searchable and retrieve-able format. | M | 24 | Product Enhancement | Concept | Trial Management | NA | X | 47 | December | NA | Complete Concept Phase (evaluate and priority/value of the project) associated with Trial Archive Implementation | Complete Concept Phase (evaluate and priority/value of the project) associated with Trial Archive Implementation | Concept Phase | As a Product Manager, I want to know the strategy to implement Site Activation Cross Trial within DD Spark System so that I am aware of its impact on context of end to end body of work that needs to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  |  |  |  | XS |  | EPL
X | B | Site Activation Enhancement | Enhance Site Activation to address new market needs/ client requriements associated to workflow design addressing onboarding, configurations, notifications and document downloads | M | 25 | External Commitment | Concept | Site Activation | Novartis/IQVIA | X | 28 | November | November | Complete Concept Phase (evaluate and priority/value of the project) associated with Site Activation Enhancements | Complete Concept Phase (evaluate and priority/value of the project) associated with Site Activation Enhancements | Con | As a Product Manager, I want to know the strategy to implement Site Activation Enhancements within DD Spark System so that I am aware of its impact on context of end to end body of work that needs to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold | [6 empty] | 000
X | B | Site Activation Enhancement (Country WF) | Enhance Site Activation to address new market needs/ client requriements associated to workflow design addressing onboarding, configurations, notifications and document downloads | M | 25 | External Commitment | Concept | Site Activation | Novartis/IQVIA | X | 29 | November | November | Complete Concept Phase (evaluate and priority/value of the project) associated with Site Activation Enhancement (Country WF) | Complete Concept Phase (evaluate and priority/value of the project) associated with Site Activation Enhancement (Country WF) . Revisit and finalize Concept considering Novartis (URS) and IQVIA |  | As a Product Manager, I want to know the strategy to implement Site Activation Enhancement (Country WF) within DD Spark System so that I am aware of its impact on context of end to end body of work that needs to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  |  |  |  | S |  | 000
X | L | Site SSO (NVS) | Lay the groundwork for implementing Site SSO for Novartis in Q1 [Mike B] | M | 22 | External Commitment | Implementation | SSO | Novartis | x |  | December | January | To connect Spark/Keycloak to Novartis's external IDP (Ping implementation), and implement on-going user management processes
| B | Trial Archive | This project is to implement a new process(es) to archive data related to a closed study to address the current lack of process to systemically archive study data from production database. Simplified process is needed to reduce strain on PS and Ops and improve responsiveness to clients. The implmentation should result in secure, validated process to request, action, and execute a full archive of all data related to a tenant and archived data is stored in a searchable and retrieve-able format. | M | 24 | Product Enhancement | Discovery | Trial Management | NA | X | 48 | December | NA | Complete Discovery Phase (evaluate and priority/value of the project) associated with Trial Archive Implementation | Complete Discovery Phase (evaluate and priority/value of the project) associated with Trial Archive Implementation | Discovery | As a Product Manager, I want to carve out Trial Archive Implementation in details to inform the granular implementation within DD Spark System so that I am aware of the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A |  |  |  |  | XS |  | EPL
| B | Trial Archive | This project is to implement a new process(es) to archive data related to a closed study to address the current lack of process to systemically archive study data from production database. Simplified process is needed to reduce strain on PS and Ops and improve responsiveness to clients. The implmentation should result in secure, validated process to request, action, and execute a full archive of all data related to a tenant and archived data is stored in a searchable and retrieve-able format. | M | 24 | Product Enhancement | Ideation | Trial Management | NA | X | 49 | December | NA | Complete Ideation Phase (Complete initial analysis in order to confirm design and architecture direction and refine estimates ) associated with Trial Archive Implementation | Complete Ideation Phase (Complete initial analysis in order to confirm design and architecture direction and refine estimates ) associated with Trial Archive Implementation | Ideation | As a Product Manager, I want to complete analysis in order to confirm design and architecture direction and refine estimates to inform Trial Archive implementation within DD Spark System so that I am able to work on its design to inform the story grooming and estimates for the product feature. Address the following: 1. List of epics 2. Refined "epic level" estimates and risks 3. Storymaps or N/A 4. Prototype and/or high level arch direction or N/A 5. Experience design or N/A |  |  |  |  | S |  | EPL
| B | Site Activation Enhancement | Enhance Site Activation to address new market needs/ client requriements associated to workflow design addressing onboarding, configurations, notifications and document downloads | M | 25 | External Commitment | Discovery | Site Activation | Novartis/IQVIA | X | 30 | November | November | Complete Discovery Phase (evaluate and priority/value of the project) associated with with Site Activation Enhancements | Complete Discovery Phase (evaluate and priority/value of the project) associated with Site Activation Enhancements | Disc | As a Product Manager, I want to carve out Site Activation Enhancements Implementation in details to inform the granular implementation within DD Spark System so that I am aware of the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A | [6 empty] | 000
| B | Site Activation Enhancement (Country WF) | Enhance Site Activation to address new market needs/ client requriements associated to workflow design addressing onboarding, configurations, notifications and document downloads | M | 25 | External Commitment | Discovery | Site Activation | Novartis/IQVIA | X | 31 | November | November | Complete Discovery Phase (evaluate and priority/value of the project) associated with Site Activation Enhancement (Country WF) | Complete Discovery Phase (evaluate and priority/value of the project) associated with Site Activation Enhancement (Country WF) . Revisit and finalize Concept considering Novartis (URS) and IQVIA |  | As a Product Manager, I want to carve out Site Activation Enhancement (Country WF) in details to inform the granular implementation within DD Spark System so that I am aware of the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A |  |  |  |  | M |  | 000
| B | Helpdesk Enhancements | Enables an extendable support system connected to the platform that allows for seamless management of support requests by internal and external administrators | M | 26 |  | Ideation | Trial Management | All | X | 50 | December | NA | We need to understand the problem associated with help desk enhancmentsto inform project scope to enable an extendable support system connected to the platform that allows for seamless management of support requests by internal and external administrators | Discovery Phase completion for Helpdesk Enhancements | Discovery Phase | Discovery Phase completion to enable an extendable support system connected to the platform that allows for seamless management of support requests by internal and external administrators. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A |  |  |  |  | XS |  | Crusher
X | B | Helpdesk Enhancements | Enables an extendable support system connected to the platform that allows for seamless management of support requests by internal and external administrators | M | 26 | Product Enhancement | Discovery | Trial Management | All | X | 51 | November | NA | We need to Complete initial analysis in order to confirm design and architecture direction and refine estimates to enable an extendable support system connected to the platform that allows for seamless management of support requests by internal and external administrators | Ideation Phase completion for Helpdesk Enhancements | Ideation Phase | Ideation Phase completion to enable an extendable support system connected to the platform that allows for seamless management of support requests by internal and external administrators. Address the following: 1. List of epics 2. Refined "epic level" estimates and risks 3. Storymaps or N/A 4. Prototype and/or high level arch direction or N/A 5. Experience design or N/A |  |  |  |  | XS |  | Crusher
X | B | Audit Trail v3 | AT V3 initiative continues to address DD Spark's performance/compliance by addressing data search and preservation | M | 27 | Platform Performance | Concept | Scalability | All | X | 52 | October | NA | With the implementation of AT V2, it is important that we revise the future AT V3 Scope to address further enahancments associated with audit trail. The business objective is to evaluate priority and value of proposed project [Concept Phase]. | Complete Concept Phase (evaluate and priority/value of the project) associated with Proposal of Audit Trail V3 | Concept Phase | As a Technical Lead and Product Manager, I want to know the strategy to address the future body of work of Audit Trail within DD Spark System so that I am aware of its impact on performance, scalability and compliance need to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  |  |  |  | XS |  | Crusher
X | L | User management for eConsent | Enable eConsent module to send User Management data and set up users of the platform [Colin M or Mike B-Please try to address what happens if we don't do it question?] | M | 28 | Internal Commitment | Concept | CTMS/Data Service | Internal | x |  | December | Mike Bassick | To allow eConsent to send User Management data and set up users of the platform | [6 empty] | Q4 (TBC) | M |  |  | In Scope | TBC
| B | Audit Trail v3 | AT V3 initiative continues to address DD Spark's performance/compliance by addressing data search and preservation | M | 27 | Platform Performance | Discovery | Scalability | All | X | 53 | October | NA | With the implementation of AT V2, it is important that we revise the future AT V3 Scope to address further enahancments associated with audit trail. The business objective is to understand the problem deeply and clarify project scope [Discovery Phase]. | Complete Discovery Phase (Understand the problem deeply and clarify project scope) associated with Proposal of Audit Trail V3 | Discovery Phase | As a Technical Lead and Product Manager, I want to know the strategy to address the future body of work of Audit Trail within DD Spark System so that I am aware of its impact on performance, scalability and compliance need to understand the problem deeply and clarify project scope. Address the following: 1. Confirm project(s) scope/goals/success criteria 2. Revise project level estimates and risks 3. Design brief or N/A 4. Architecture brief or N/A |  |  |  |  | S |  | Crusher
x | L | DQS - Sendgrid integration | Integrate DQS with Sendgrid | M | 29 | Internal Commitment/Performance | Concept | CTMS/Data Service | IDB/TrC Members | x |  | December | Mike Bassick | Allow e-mails to be sent directly from sendgrid which relays them. Because Sendgrid vets the e-mails, this means there is a higher probability of our e-mails being received (rather than filtered). | [6 empty] | Q4 2018 | M |  |  | In Scope | Kirithika
X | L | eFeasibility SSO | In partnership with CTOS team, complete Concept and Design to prepare for Implementation of Profiles in the tool in Q2 [Mike B] | L | 31 |  | Concept | SSO | Mike Bassick | x |  | L - December | Mike Bassick
X | L | Sponsor SSO (VRTX) | N/A - likely Q1 implementation | L | 33 | External Commitment | Implementation | SSO | Vertex | x |  | December | Mike B | To connect Spark/Keycloak to Vertex's internal IDP
X | B | Audit Trail v4 | AT v4 will redirect platform writes to use new AT MS instead of MySQL. We have runway through the end of 2019 to complete this. | M | 30 | Platform Performance | Concept | Scalability | All | x |  | October | NA | Reduce burden on platform DB and normalize how we write to Audit Trail across platform and all microservices. | Complete Concept Phase. | Concept Phase | As a Technical Lead and Product Manager, I want to know the strategy to address the future body of work of Audit Trail within DD Spark System so that I am aware of its impact on performance, scalability and compliance need to evaluate and priority/value of the project. Address the following: 1. Business Justification (Submission Gate) 2. Outline of project scope/goals 3. Identify constraints or risks 4. Initial project level estimates 5. UX vision mockups or N/A 6. Business decision to schedule or put on hold |  |  |  |  | XS |  | Crusher
X | L | Profiles SSO | Complete Concept and Design to prepare for Implementation in Q1 [Mike B] | L | 34 |  | Concept | SSO | Investigators | x |  | L - December | Q2 | To connect Spark/Keycloak to Connect/DD Profiles so that investigators can create/manage profile information from Spark
X | L | DQS SSO | Complete Concept and Design to prepare for Implementation in Q1 [Milke B] | L | 35 |  | Concept | SSO | IDB/TrC Members | x |  | L - December | Q2
|  | Doc Library Cleanup |  |  |  |  | Implementation |  |  |  |  | October |  |  | Complete Removal of Paperclip from Document Library related code | Doc Library Cleanup | Largely QA effort remaining |  |  |  |  | M |  | 000

## Q418-Lon Qtr Plan (hidden)
Priority | Rank | Initiatives | Description | Category | Phase | Internal Delivery | Customer Delivery | # Sprints | Weeks | Months | Comments | Resource | Added to wall
H | 1 | Infrastructure - Ubuntu upgrade | Upgrade all servers to latest version of Ubuntu. This ensures we comply with our audit guidelines by running up to date software with latest patches. Dockers + Kuebernetes. Must complete w/ in 6 months | Internal commitment | Implementation | December | NA: XL+ | 12 | 24 | 6 |  | John | Y
H | 4 | Profiles - Connect Tech Debt | Front End Technical debt, all components will need to be re-factored and upgraded. This is first major upgrade required to keep F.E. up to date since and compliance since launch. Should be done in tandem w/ automated testing. CTMS is a higher priority for automated testing capacity | Internal commitment | Implementation | September | NA: XL+ | 12 | 24 | 6 | Conflict exists for QA, until more QA resource is available | Tim (FE) Ian - Conflict | Y
C | 1 | IR for SIP 3.1 | Complete development and testing for new IR endpoints for SIP R3.1 In Q4, we will be assisting Cognizant integration testing in the new IR endpoints for multiple city and state searching and filtering. | External Commitment | Implementation | October | October: XS | 1 | 2 | 0.5 |  |  | Y
C | 1 | Curation Tool for SIP 3.1 | Make changes in curation tool to allow a Golden Facility to be created without it needing to be associated to a person | External Commitment | Implementation | Oct: XS | TBC by Feb 23 | 1 | 2 | 0.5 |  | Vince | N/A
[5 empty] | Implementation | 15th Dec (Ideal by Int Test): S |  | 2 | 4 | 1 |  | Tim | Y
H | 3 | Test Automation CTMS | Continued test automation for all tools. CTMS is initial priority. Some technical difficulties w/ VPN. | Internal Commitment | Implementation | Dec: L | NA | 4 | 8 | 2 |  | Ian? | Y
M | 5 | Test Automation for IR (Q1) | Continued test automation for all tools. IR is the second priority. Some technical difficulties w/ VPN. | Internal Commitment | Concept/ Implementation | TBD: XL | TBD | 6 | 12 | 3 |  | Ian? | Y
H | NA | DQS Refactoring / Tech Debt | This is a catchall for any other technical debt required in DQS - it will be expanded as Q4 progresses. Ideally, would be paired w/ automated testing. This includes search optimization & indexer changes. Needs to be broken out into activities and ROI. | Internal commitment | Concept / Analysis - M | January | NA: | 6 | 12 | 3 | - Indexer & SendGrid - Q4 for Analysis |  | Y (tentatively for Jan)
M | 6 | DQS - SendGrid integration | Integrate DQS with SendGrid for mail proxy (relates to DQS refactorying/technical debt). One action in the bigger Epic | Internal Commitment | Concept/ Implementation | December/ Jan | M | 3 | 6 | 1.5 |  | Clement | Y | Clarify status with Clement
C | 4 | Site SSO (Core) | Implement the logic and user flows related to site-based users of Spark, accounting for multiple sponsor IDPs, so that we will be ready to deliver on enterprise customer commitments in Q1/19. | External Commitment | Design & Implementation | December: M Note: Could slip if Janssen slips | NA | 3 | 6 | 1.5 | Conflict due to Ubuntu upgrade activity (John's assignment) Dependent on JnJ's steer | John | Y
C | 8 | Front End User Management Tools | Development of Front-end user tools so that Enterprise customers edits are managed in coordination with Platform CTMS functionality. Goal is to finish one-pager | External Commitment | Concept | October: XS | NA | 1 | 2 | 0.5 |  | Tracy | Y
C | 8 | Front End User Management Tools | Development of Front-end user tools so that Enterprise customers edits are managed in coordination with Platform CTMS functionality. Boston dependency TBD (permissions) | External Commitment | Disovery/ Ticket | TBD Triage Nov: S | TBD | 2 | 4 | 1 |  | Tracy | Y
C | 8 | Novartis Go-Live on SUM (site and non-site) | Novartis launch on SUM. Dependency on Automation Testing – higher priority than Test Automation for IR | External Commitment | Implementation | Oct: S | Oct | 2 | 4 | 1 |  | Tracy | Y
C | New | IQVIA CTMS Sponsor | Changes in support of splitting Data Source vs. Customer Secret Token. Investigate whether needs to be completed in Q4 | Internal | Concept | Concept: done | TBD Q4 |  |  |  | Needs to be discussed further |  | N/A
|  |  |  | Commitment |  | Impl: M |  | 3 | 6 | 1.5 |  |  | N
H | 14 | IQVIA SSO | Resolve email address mismatch issues between all CTMS and front-end tool sources of @quintiles and @iqvia emails. Implemention will be blocked on front-end user tools | External Commitment | Concept/ Discovery | Oct/Nov: S | TBD | 2 | 4 | 0.5 |  | Mike / John | Y
C |  | BI Onboarding CTMS | Primarily BA work, but on-boarding will require changes to create VPD, importer, DQS, sharing rules, etc. Colin to determine timing | External Commitment | Concept (XS) | Q4? Implement: Q1 | TBD |  |  |  |  | Colin / Tracy | Y - but likely to move to Q1 19
M |  | CS-API SUM | We need to be able to accept real-time api calls in the future. Likely starting with NVS, but the implementation should be customer-agnostic | Internal Commitment | Concept/Discovery | December: S | H1 19 likely |  |  |  |  | Tracy / Mahdi 1 | Y
C |  | CS-API: Move Facility details from SUM to Site endpoint | This is urgently required in order to keep the data consistent, which is needed for Safety. Ideally, we get it done for v1.5.5, but if there isn't enough time to test it, this can wait. If it waits, there has to be some data cleaning afterwards. But again better well tested than rushing it and putting us in a worse situation than before. |  | Implementation | 1.5.5. hopefully: S | N/A | 2 | 4 | 1 |  | Tracy | Y
|  | CTMS integration non-site bug fix | Non-site file fix
M | 21 | Site SSO Janssen | Janssen integration w/ Exostar for SSO. Dependent on Site SSO Core. Blocked on signing of Exostar agreement. Solution assumes customer is responsible for provisioning. | External Commitment | PoC | Janssen have pushed this to Q1/Jan | TBD
M | 28 | eConsent User management | Enable eConsent module to send User Management data and set up users of the platform. Discover at F2F | Internal Commitment | Concept | December/Q1 | December/Q1
L | 31 | eFeasibility SSO | In partnership with CTOS team, complete Concept and Design to prepare for Implementation of SSO in the tool in Q2 19 | Internal Commitment | Concept | Q1 | Q1
L | 33 | Sponsor SSO (VRTX) | N/A - likely Q1 implementation | External Commitment | Implementation | TBD | TBD
L | 34 | Profiles SSO | To connect Spark/Key cloak to Connect/DD Profiles so that investigators can create/manage profile information from Spark. eFeasibility w/ Profiles Q4 19 launch. Dependency on DQS SSO – must happen in tandem. Handover | Internal Commitment | Concept/ Design | Dec/Jan | NA
L | 35 | DQS SSO | To connect Spark/Key cloak to DQS so that users can authenticate using their company credentials. Dependency on Profiles SSO – must happen in tandem. Handover | Internal Commitment | Concept/ Design | Dec/Jan | NA
|  | eConsent SSO | Connect eConsent into the KeyCloak SSO. Ideally happen w/ IQVIA SSO. Question: implications for Lilly Identity Hub |  |  | Not Q4 | Not Q4
|  | Initiative | Description and plan
|  | Connect Tech Debt | Potential Conflict: Do we progress Connect tech debt without QA resource? Or do we wait until new QA starts in Nov? Proposed plan: We expedite SIP curation tool change first, dev starts asap. This buys time before new QA and Leire start in Nov. Issues: Still likely a FE gap that needs to be filled with work before connect could start. Tim could likely assist with some of the high-priority testing work.
|  | DQS vs Site SSO | Potential Conflict: Site SSO dates TBC. Do we get Mahdi 2/Clement progressing the handover for DQS or SSO Proposed Plan: Mahdi 2/Clement start on DQS handover. Bug tickets already started work this sprint. Once Site SSO dates are clarified, we transition them off DQS in advance. Depending on when this is, it may impact indexr optmisation implementation.
|  | Vince | No work allocated after mid Oct (aside from supporting integration testing)

## Pivot Table 1 (hidden)
Team | Initiative
Doc Library Cleanup
Total
B | Apollo Design System Adoption
Audit Trail v2
Audit Trail v3
Audit Trail v4
Clin Tech Navigation
Cross Trial Reporting
CrossTrial LMS (2.1)
Delegation Log v2
eSig
eTMF API Delivery V1
eTMF API Delivery V2
Helpdesk Enhancements
Scalability and Performance
Search
Site Activation Cross Trial
Site Activation Enhancement
Site Activation Enhancement (Country WF)
Site Activation Reporting
Trial Archive
Versioning and Equivalence
B Total
L | DQS - Indexer Optimisation
DQS - Sendgrid integration
DQS Refactoring/Tech Debt
DQS SSO
eFeasibility SSO
Front End User Management Tools
Infrastructure - Ubuntu upgrade
Investigator Registry NR
IQVIA CTMS and SSO
IR for SIP 3.1
Profiles - Connect Tech Debt
Profiles SSO
Site SSO (Core)
Site SSO (JAN)
Site SSO (NVS)
Sponsor SSO (VRTX)
User management for eConsent
L Total
(blank) | CrossTrial LMS 2.0 Support
Site Activation Reporting
(blank) Total
Grand Total

## Test_Reporting (hidden)
Initiative | Phase |  | Month | Team
eTMF API Delivery V1 | Implementation | 1 | October | EPL & 000
Site Activation Reporting | Implementation | 1 | October | 000
Versioning and Equivalence | Implementation | 3 | December | slamina
CrossTrial LMS 2.0 Support | 0 |  | 0 | 0
CrossTrial LMS (2.1) | Implementation | 2 | November | slamina
Audit Trail v2 | Implementation | 1 | October | Crusher
Delegation Log v2 | Discovery | 3 | L - December | slamina
eTMF API Delivery V2 | Ideation | 3 | December | EPL
Audit Trail v3 | Implementation | 2 | November | Crusher
Site SSO (Core) | Ideation | 3 | December | 0
Cross Trial Reporting | Concept | 2 | November | 000
Scalability and Performance | 0 |  | 0 | 0
eSig | Concept | 1 | October | slamina
Search | Ideation | 3 | December | EPL
Front End User Management Tools | Discovery | 0 | September | 0
Site Activation Cross Trial | Concept | 2 | November | 000
IQVIA CTMS and SSO | Implementation | 3 | December | 0
DQS - Indexer Optimisation | Concept | 3 | December | 0
Infrastructure - Ubuntu upgrade | Implementation | 3 | December | 0
Profiles - Connect Tech Debt | Implementation | 3 | December | 0
DQS Refactoring/Tech Debt | Concept | 2 | November | 0
Clin Tech Navigation | Concept | 3 | December | slamina
IR for SIP 3.1 | Implementation | 3 | December | 0
Apollo Design System Adoption | Discovery | 3 | December | slamina
Site SSO (JAN) | Implementation | 3 | December | 0
Trial Archive | Concept | 3 | December | EPL
Site Activation Enhancement | Concept | 2 | November | 000
Site Activation Enhancement (Country WF) | Concept | 2 | November | 000
Site SSO (NVS) | Implementation | 3 | December | 0
Helpdesk Enhancements | Ideation | 3 | December | Crusher
User management for eConsent | Concept | 3 | December | 0
DQS - Sendgrid integration | Concept | 3 | December | 0
eFeasibility SSO | Concept | 3 | L - December | 0
Sponsor SSO (VRTX) | Implementation | 3 | December | 0
Audit Trail v4 | Concept | 2 | October | Crusher
Profiles SSO | Concept | 3 | L - December | 0
DQS SSO | Concept | 3 | L - December | 0
Doc Library Cleanup | Implementation | 2 | October | 000

## Wall Planning (Q4)
|  |  | Q3 | [11 empty] | Q4
| Focus | Sprint # | 26 | 27 | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 HOLIDAY |  | 37 |  | 38 HOLIDAY
|  | Sprint Start | 2020-06-29 | 2020-07-13 | 2020-07-27 |  | 2020-08-10 |  | 2020-08-24 |  | 2020-09-07 |  | 2020-09-21 |  | 2020-10-05 |  | 2020-10-19 |  | 2020-11-02 |  | 2020-11-16 |  | 2020-11-30 |  | 2020-12-14
|  | Sprint End | 2020-07-10 | 2020-07-24 | 2020-08-07 |  | 2020-08-21 |  | 2020-09-04 |  | 2020-09-18 |  | 2020-10-02 |  | 2020-10-16 |  | 2020-10-30 |  | 2020-11-13 |  | 2020-11-27 |  | 2020-12-11 |  | 2020-12-18
Eredivisie | Lead | Akshay |  |  | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support |  | Tier 2 | Tier 2 | Tier 2 | Tier 2 | Tier 2 | Tier 2 |  | Tier 2 | Tier 2 | Tier 2
| Server | Chandan |  |  | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | Trim input strings in CDOS | Tier 2 | Tier 2 | Update export Excel Version | Update export Excel Version | Update export Excel Version | Tier 2 |  | Tier 2 | Tier 2 | Tier 2
| Dev | Niranjan |  |  | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Increase RT | Tier 2 | Persisting User Selections | Persisting User Selections | FSS Date - when FSIV has occurred | Tier 2 | Tier 2 |  | Tier 2 | Tier 2 | Tier 2
| Triage |  |  |  | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support
| DB | Akshay |  |  | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 |  | Tier 2 | Tier 2 | Tier 2 | Tier 2 | Tier 2 | Tier 2 |  | Tier 2 | Tier 2 | Tier 2
| Triage |  |  |  | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support
| QA | Nidhi |  |  | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab MCE View Functionality Missing in 6.0/6.1 |  | Tier 2 | Restore CRD Options | Restore CRD Options | Restore CRD Options | FSS Date - when FSIV has occurred | Tier 2 |  | Tier 2 | Tier 2
| Triage |  |  |  | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support | On-Going Tier 2 Application Support
Bundesliga | Dev | Gui |  |  | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | SAS Calculation | SAS Calculation | SAS Calculation | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Parent cohort not defined - error msg | Parent cohort not defined - error msg | Adjustment – MCS auto populate min # of sbj |  | Updated SAS Calculation | Updated SAS Calculation
| Lead |  |  |  | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead |  | Lead | Lead | Lead
| Server | Deepa |  |  | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | SAS Calculation | SAS Calculation | SAS Calculation | SAS Calculation | SAS Calculation | Associate HA Visual Indicators | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Parent cohort not defined - error msg | Adjustment – MCS projected contributing sites < 1 |  | 1. OpenJDK Adoption (EB) | Produciton Monitoring | Produciton Monitoring
| DB | Amar / Rahul (as needed) |  |  | Adobe Flash Refactor, Phase 2 - EB (6.1) | Merck Changes to Data Virtualization | Merck Changes to Data Virtualization | Merck Changes to Data Virtualization | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | SAS Calculation | SAS Calculation | SAS Calculation | Create Plans: R-type / S-type - Rahul (50%) | Create Plans: R-type / S-type - Rahul (50%) | Create Plans: R-type / S-type - Rahul (50%)
| UI | Lalit |  |  | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Rate Adjustments | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Rate Adjustments | SAS Calculation | Associate HA Visual Indicators | Associate HA Visual Indicators | Associate HA Visual Indicators | Associate HA Visual Indicators | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Adjustment – MCS projected contributing sites < 1 |  | Adjustment – MCS projected contributing sites < 1 | Updated SAS Calculation | Updated SAS Calculation
| QA Lead | Madhu |  |  | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Rate Adjustments | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Rate Adjustments | SAS Calculation |  |  |  |  | Parent cohort not defined - error msg | Parent cohort not defined - error msg
`
| QE | Harshalatha | [12 empty] | Trim input strings in CDOS | Associate HA Visual Indicators | Associate HA Visual Indicators | Associate HA Visual Indicators | Persisting User Selections | Persisting User Selections
| QE | Priyanka |  |  | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor, Phase 2 - EB (6.1) | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Associate HA | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Rate Adjustments | Adobe Flash Refactor Phase 3 - Postponed Features - Plans Tab Rate Adjustments |  | 1. OpenJDK Adoption (EB) | Increase RT | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Create Plans: R-type / S-type | Adjustment – MCS auto populate min # of sbj |  | Adjustment – MCS projected contributing sites < 1 | Updated SAS Calculation | Updated SAS Calculation
Premier League | Dev | Janhavee |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Rollout Activities - Packaging for Deployment | Rollout Activities - Packaging for Deployment | Rollout Activities - Packaging for Deployment | Rollout Activities - UAT | Phase 3- DCP View Functionality | Phase 3- DCP View Functionality | Phase 3- DCP View Functionality | Phase 3- DCP View Functionality |  |  | Backlog | Backlog | Backlog | Backlog | Backlog | Backlog |  | Backlog | Backlog | Backlog
| Triage | [8 empty] | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects |  |  |  |  | Update export Excel Version | Update export Excel Version | Update export Excel Version
| Dev | Rahul |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Rollout Activities - Packaging for Deployment | Rollout Activities - Packaging for Deployment | Rollout Activities - Packaging for Deployment | Rollout Activities - UAT | Phase 3- DCP View Functionality | [5 empty] | Backlog | Backlog | Backlog | Backlog | Backlog | Backlog |  | Backlog | Backlog | Backlog
| Triage | [8 empty] | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects |  |  |  |  | 1. Ora 19C Upgrade (EB Service) | 1. Ora 19C Upgrade (EB Service) | Backlog | Backlog |  | Backlog | Backlog | Backlog
| Dev | Vamshi |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Adobe Flash Refactor Phase 3 - Postponed Features - DCP View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - DCP View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - DCP View Functionality Missing in 6.0/6.1 | Rollout Activities - UAT | Phase 3- DCP View Functionality | Phase 3- DCP View Functionality | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add |  |  | Backlog | Backlog | Backlog | Backlog | Backlog | Backlog |  | Backlog | Backlog | Backlog
| Triage | [8 empty] | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects
| QE | Anisa |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Adobe Flash Refactor Phase 3 - Postponed Features - DCP View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - DCP View Functionality Missing in 6.0/6.1 | Adobe Flash Refactor Phase 3 - Postponed Features - DCP View Functionality Missing in 6.0/6.1 | Rollout Activities - UAT | Phase 3- DCP View Functionality | Phase 3- DCP View Functionality | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add |  |  | Backlog | Backlog | Backlog | Backlog | Backlog | Backlog |  | Backlog | Backlog | Backlog
| Triage | [8 empty] | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects | Rollout Activities - Show Stopper Defects
Serie A | Dev | Swapnil |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add | Plans Tab - Rate Adj Templates | Restore CRD Options | Restore CRD Options | Restore CRD Options | Restore CRD Options | Adjustment - abiliy to use approved plan rates | Adjustment - abiliy to use approved plan rates |  | Adjustment - abiliy to use approved plan rates | Adjustment - abiliy to use approved plan rates
| Lead |  |  |  | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead
| Server | Sidharam |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add | Plans Tab - Rate Adj Templates | Restore CRD Options | Restore CRD Options | Adjustment – Solve for # of Subjects | Adjustment – Solve for # of Subjects | Adjustment – Solve for # of Subjects | Adjustment – Solve for # of Subjects |  | Adjustment - abiliy to use approved plan rates | Adjustment - abiliy to use approved plan rates
| DB | Amar |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Merck Changes to Data Virtualization | Merck Changes to Data Virtualization | Merck Changes to Data Virtualization | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments |  | Update export Excel Version | Update export Excel Version | Update export Excel Version | Update export Excel Version | Update export Excel Version | Update export Excel Version | Update export Excel Version |  | Update export Excel Version | Produciton Monitoring | Produciton Monitoring
|  | Sri | [12 empty] | Restore CRD Options | Restore CRD Options | Restore CRD Options | Restore CRD Options
| UI | Sachin |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add | Plans Tab - Rate Adj Templates | Plans Tab - Rate Adj Templates | Plans Tab - Rate Adj Templates | Adjustment – Solve for # of Subjects | Adjustment – Solve for # of Subjects | Adjustment – Solve for # of Subjects | Adjustment – Solve for # of Subjects |  | Adjustment - abiliy to use approved plan rates | Usage Analytics | Usage Analytics
| QA Lead | Madhu |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add
|  | Harshalatha | [18 empty] | Update export Excel Version |  | Update export Excel Version | Update export Excel Version | Update export Excel Version | Update export Excel Version | Update export Excel Version
| QA | Namita |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - View | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Create New | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Edit | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Analysis Tab - Rate Adjustment Template List - Manage Rate Adjustments | Adobe Flash Refactor Phase 3 - Plans Tab - Rate Adjustment Template - Add | Plans Tab - Rate Adj Templates | Plans Tab - Rate Adj Templates | Plans Tab - Rate Adj Templates | Adjustment - abiliy to use approved plan rates | Adjustment – Solve for # of Subjects | Adjustment – Solve for # of Subjects | Adjustment – Solve for # of Subjects |  | Adjustment - abiliy to use approved plan rates | Adjustment - abiliy to use approved plan rates | Adjustment - abiliy to use approved plan rates
La Liga | Architect | Sunil |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Algorithm Microservices Architecture - High-Level Architecture | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Move to Independent Project 25% | Algorithm Microservices Architecture - Move to Independent Project 25% | Algorithm Microservices Architecture - Move to Independent Project 25% | Algorithm Microservices Architecture - Move to Independent Project 25% | Algorithm Microservices Architecture - Move to Independent Project 25% | AWS : Containarization & repository | k8s : AWS cost analysis high level analysis | k8s: AWS EKS Network settings | Security for Microservices | k8s :Monitoring & Reliability | k8s: Log aggregation | Review | Review | Review | Review | Review | Review
| Lead |  |  |  | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF | DDF
| Server | Lokesh |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Algorithm Microservices Architecture - High-Level Architecture | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Deployment | Algorithm Microservices Architecture - Deployment | k8s: AWS EKS Fargate infrastructure | k8s: AWS EKS Fargate infrastructure | k8s: Springboot native k8s project change | k8s: Springboot native k8s project change | k8s: Ingress & Ingress controller | k8s: Ingress & Ingress controller | Security for Microservices | k8s: configurations (configMaps) & Persist volumes | k8s: configurations (configMaps) & Persist volumes | k8s: Log aggregation | k8s: Log aggregation
| Lead |  |  |  | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead | Lead
|  | Shrikesh |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Algorithm Microservices Architecture - High-Level Architecture | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Move to Independent Project | Algorithm Microservices Architecture - Deployment | Algorithm Microservices Architecture - Deployment | AWS : Containarization & repository | AWS : Containarization & repository | Jenkins job to push image into repository | Security for Microservices | k8s: AWS EKS EC2 infrastructure | k8s: AWS EKS EC2 infrastructure | k8s: Springboot Eureka (OSS) project changes | k8s: Springboot Eureka (OSS) project changes | k8s: Deployment scripts | k8s: Deployment scripts | k8s : Tracing | k8s : Tracing
| DB | Sri |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Merck Changes to Data Virtualization | Merck Changes to Data Virtualization | Merck Changes to Data Virtualization | Adobe Flash Refactor Phase 3 - Postponed Features - Setting Cohort Readiness Date | Adobe Flash Refactor Phase 3 - Postponed Features - Setting Cohort Readiness Date | Adobe Flash Refactor Phase 3 - Postponed Features - Setting Cohort Readiness Date | Adobe Flash Refactor Phase 3 - Postponed Features - Setting Cohort Readiness Date | [6 empty] | k8s :Monitoring & Reliability | k8s :Monitoring & Reliability | k8s :Monitoring & Reliability
| QA Lead | Amit Panda |  |  | Adobe Flash Refactor, Phase 2 - Countries, Studies, Sites, Study List/Runway, EB (6.1) | Merck Changes to Data Virtualization | Merck Changes to Data Virtualization | Merck Changes to Data Virtualization | Adobe Flash Refactor Phase 3 - Postponed Features - Setting Cohort Readiness Date | Adobe Flash Refactor Phase 3 - Postponed Features - Setting Cohort Readiness Date | Adobe Flash Refactor Phase 3 - Postponed Features - Setting Cohort Readiness Date | Adobe Flash Refactor Phase 3 - Postponed Features - Setting Cohort Readiness Date |  |  |  |  | Test strategy & data Preparation | Performance Test strategy & data preparation | Auto scaling/HA/resilient testing strategy | Test Algorithm Microservcie on Kubernetes | Load Test ing of Algorithm Microservcie on Kubernetes | Auto Scaling Test for Algorithm Microservcie on Kubernetes | HA testing of Algorithm Microservice on K8s

## EC Priortization
Initiative | BO Priority (C,H,M,L) | Stack Rank | EPIC ID | BO Summary | BO- Description | Story Stubs | BO- T-Shirt Size (Dev) | Development Sequence | Scrum Team | Product Lead | Dev Lead | Dev and QA Complete | In Scope | Planned
CRD | C |  | ST-5400 | Restore CRD Options | What: Restore user ability to set a Cohort Readiness Date Why: In 6.0 we attempted to handle this via code logic. This approach resulted in exaggerated rates for a large subset of studies, we were not successful. To produce accurate rates and enable proper planning, this feature must be returned. Outcome: Cohort Actual Rates and projections are calculated based on user provided readiness dates | 1. Manage Cohorts - CRD Options (SI, Enrollment/Screening) 2. CRD - SI Behavior 3. CRD - Screening (S-Type) behavior 4. CRDE - Enrolling (R-Type) behavior 5. Countries Tab - Cohort Performance View -- CRD Value 6. Countries Tab - Country Performance View -- CRD Value 7. Sites Tab - Enrollment Details - CRD Value | L | 1 | Serie A | Tony | Swapnil (Sri [La Liga] DB) |  | 6.1.2
Tech Debt | C |  | ST-2543 | OpenJDK (EB) | Corporate Mandate | 1. OpenJDK Adoption (EB) | xs | 1 | Bundesliga | Sandeep | Gui |  |  | Yes
Tech Debt | C |  | ST-2543 | Ora 19c (EB) | Oracle end of support | 1. Ora 19C Upgrade (EB Service) | xs | 1 | Bundesliga | Sandeep | Gui |  |  | Yes
Tech Debt | H |  | ST-2543 | Produciton Monitoring | What: Setup AWS monitoring Why: Inform tech staff of outages Outcome: internal staff aware of outage prior to customer | 1. Monitoring for Production outage | m | 7 | Bundesliga | Sandeep | Gui |  |  | Yes
Tech Debt | H |  | ST-2543 | Usage Analytics | What: track applicatoin usage (e.g datadog) Why: understand how and when in the app is used Outcome: actionable data | N/A - architecture research | s | 8 | Arun | Sandeep | Gui |  |  | Yes
Tech Debt | M |  | ST-2543 | Trim input strings | What: Remove preceeding and trailing "spaces" from input string Why: Outcome: | 1. Trimming the string for all input text fields from UI at CDOS | xs | 1 | Eredivisie | Tony | Akshay |  |  | Yes
Tech Debt | C |  | ST-5762 | Update export Excel Version | What: Upgrade reporting engine Why: To allow more than 256 column in an export Outcome: accurate exports | 1. Jasper report engine upgrade 2. Reports truncate after column IV (256 columns) | L (lots of testing) | 2 | Serie A | Jo | Swapnil |  |  | Yes
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | see EC Prioritization (MicroSrv) tab | 4th Q | see EC Prioritization (MicroSrv) tab | La Liga | John | Lokesh |  |  | Yes
Adobe Refactor (Phase 3) | H |  | ST-5174 | Plans Tab - Rate Adj Templates | What: Restore RA template feature Why: Prevent loss of feautre from Adobe Refactor Outcome: restored feature | 1. Select RA Template 2. Application Restrictions 3. Apply Selected Template | m | 1 | Serie A | Jo | Swapnil |  |  | Yes
Adobe Refactor (Phase 3) | H |  | ST-4818 | Associate HA Visual Indicators | What: Restore HA association feature Why: Prevent loss of feautre from Adobe Refactor Outcome: restored feature | 1. Hide/Display Historic List - Multi-Country View 2. Visual Indicator IC View - Sites Actively Screening 3. Visual Indicator IC View - Days from FSI to FSS 4. Visual Indicator IC View - FPA to FSI 5. Visual Indicator IC View - Site Initiation | m | 1 | Bundesliga | Jo | Gui |  |  | yes
UX Improvements | H |  | ST-1955 | Updated SAS Calculation | What: Improve SAS Cal approach Why: Customer demand Outcome: Reduction in support calls | 1. SAS calculation changes | m | 3 | Bundesliga | Tony | Gui |  |  | yes
UX Improvements | H |  | ST-1955 | Increase RT | What: Increase max RT Why: Customer demand Outcome: Ability to plan for larger trials (i.e. covid) | 1. Increase RT to 150K | xs | 1 | Eredivisie | Jo | Akshay |  |  | Yes
UX Improvements | C |  | ST-1955 | Create Plans: R-type / S-type | What: Modify "create plan type" options Why: Streamline creation of R-type cohort plans Outcome: ability to create all 3 plans types without going into CDOS | 1. Create Plan – R-Type and S-Type Options | m | 2 | Serie A | Tony | Swapnil |  |  | Yes
UX Improvements | H |  | ST-1955 | Parent cohort not defined - error msg | What: Improve error message handeling Why: accuratly Inform users of issue Outcome: Reduction in support calls | 1. Error Message - Parent Cohort Not completely defined | s | 6 | Bundesliga | Tony | Gui |  |  | yes
UX Improvements | M |  | ST-74 | Persisting User Selections | What: Maintian user selections / preferances Why: Customer demand Outcome: Better useability | 1. Study Tab - Enrollment View - persist hide/display selection of grid/graph view 2. Study Tab - Study Milestones - persist hide/display selection of grid/graph view 3. Study Tab - Reports - persist hide/display selection of grid/graph view 4. Country Tab - Country Performance - persist hide/display selection of grid view 5. Country Tab - Cohort Performance - persist hide/display selection of grid view 6. Multi-Country Edit - persist hide/display selection of grid view | s | 2 | Eredivisie | Jo | Akshay |  |  | Yes
Plan Adjustment Improvements | H |  | ST-1702 | Adjustment - abiliy to use approved plan rates | What: Ability to use approved plan rates in adjustments Why: Customer Demand Outcome: Ability to use approved plan rates in adjustments | 1. DCP view Reset Algorithm using Approved Plan values 2. MCE View - Reset Algorithm using Approved Plan values | m | 2 | Bundesliga | Tony | Gui |  |  | yes
Plan Adjustment Improvements | H |  | ST-1702 | FSS Date - when FSIV has occurred | What: Improve error message handeling Why: accuratly Inform users of issue Outcome: Reduction in support calls | 1. FSS Date - when FSIV has occurred | xs | 3 | Eredivisie | Jo | Akshay |  |  | Yes
Plan Adjustment Improvements | H |  | ST-1702 | Adjustment – MCS projected contributing sites < 1 | What: Improvement to Optimal Subject sovler Why: Customer demand Outcome: When< 1 site is projected to contribute, no error is thrown | 1. Adjustment – MCS projected contributing sites < 1 | s | 4 | Bundesliga | Tony | Gui |  |  | yes
Plan Adjustment Improvements | H |  | ST-1702 | Adjustment – MCS auto populate min # of sbj | What: Auto populate min sbj when actuals are present Why: Customer demand Outcome: | 1. Adjustment – MCS minimum # of subjects | xs | 5 | Bundesliga | Jo | Gui |  |  | yes
Plan Adjustment Improvements | H |  | ST-1702 | Adjustment – Solve for # of Subjects | What: Add subject solver to plan adjustment solvers Why: Customer demand Outcome: | 1. Adjustment – Solve for # of Subjects | m | 3 | Serie A | Jo | Swapnil |  |  | Yes
[6 empty] | Serie A | 5 | L,L,m,m,m
[6 empty] | Bundesliga | 9
[6 empty] | Eredivisie | 4
[6 empty] | La Liga | 1

## EC Priortization (MicroSrv)
Initiative | BO Priority (C,H,M,L) | Stack Rank | EPIC ID | BO Summary | BO- Description | Story Stubs | BO- T-Shirt Size (Dev) | Development Sequence | Scrum Team | Product Lead | Dev Lead | Dev and QA Complete | In Scope
CRD | C |  | ST-5400 | Restore CRD Options | What: Restore user ability to set a Cohort Readiness Date Why: In 6.0 we attempted to handle this via code logic. This approach resulted in exaggerated rates for a large subset of studies, we were not successful. To produce accurate rates and enable proper planning, this feature must be returned. Outcome: Cohort Actual Rates and projections are calculated based on user provided readiness dates | 1. Manage Cohorts - CRD Options (SI, Enrollment/Screening) 2. CRD - SI Behavior 3. CRD - Screening (S-Type) behavior 4. CRDE - Enrolling (R-Type) behavior 5. Countries Tab - Cohort Performance View -- CRD Value 6. Countries Tab - Country Performance View -- CRD Value 7. Sites Tab - Enrollment Details - CRD Value | L
Tech Debt | C |  | ST-2543 | OpenJDK (EB) | Corporate Mandate | 1. OpenJDK Adoption (EB) | xs
Tech Debt | C |  | ST-2543 | Ora 19c (EB) | Oracle end of support | 1. Ora 19C Upgrade (EB Service) | xs
Tech Debt | H |  | ST-2543 | Produciton Monitoring | What: Setup AWS monitoring Why: Inform tech staff of outages Outcome: internal staff aware of outage prior to customer | 1. Monitoring for Production outage | m
Tech Debt | H |  | ST-2543 | Usage Analytics | What: track applicatoin usage (e.g datadog) Why: understand how and when in the app is used Outcome: actionable data | N/A - architecture research | s
Tech Debt | M |  | ST-2543 | Trim input strings | What: Remove preceeding and trailing "spaces" from input string Why: Outcome: | 1. Trimming the string for all input text fields from UI at CDOS | xs
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | AWS : Containarization & repository | s+xs |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | Jenkins job to push image into repository | xs |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: AWS EKS EC2 infrastructure | S |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: AWS EKS Network settings/configurations | s |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: AWS EKS Fargate infrastructure | S |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s : AWS cost analysis high level analysis | xs |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: Ingress & Ingress controller | S |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: configurations (configMaps) & Persist volumes | S |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: Springboot Eureka (OSS) project changes | xs |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: Springboot native k8s project change | xs |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: Deployment scripts | S |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s :Monitoring & Reliability | M |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s: Log aggregation | s+xs |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | k8s : Tracing | S |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | Security for Microservices | S |  | La Liga
Algorithm Microservice Architecture | C |  | ST-4923 | Microservice Arch | What: Achieve auto orchestration of Algorithm microservice Why: pre-work for MC Outcome : deploy algorithm microservice in AWS EKS | DevOps |  |  | La Liga
Adobe Refactor (Phase 3) | H |  | ST-5174 | Plans Tab - Rate Adj Templates | What: Restore RA template feature Why: Prevent loss of feautre from Adobe Refactor Outcome: restored feature | 1. Select RA Template 2. Application Restrictions 3. Apply Selected Template | m
Adobe Refactor (Phase 3) | H |  | ST-4818 | Associate HA Visual Indicators | What: Restore HA association feature Why: Prevent loss of feautre from Adobe Refactor Outcome: restored feature | 1. Hide/Display Historic List - Multi-Country View 2. Visual Indicator IC View - Sites Actively Screening 3. Visual Indicator IC View - Days from FSI to FSS 4. Visual Indicator IC View - FPA to FSI 5. Visual Indicator IC View - Site Initiation | m
UX Improvements | M |  | ST-4640 | MCE/MC - Cohort TSLR date | What: Inform user when Cohort RT are not being met Why: Enable proper planning Outcome: Reduction in support calls | 1. Manage Countries View – Cohorts – Display Cohort TLSR date 2. Multi-Country Edit Cohorts - display cohort TLSR date from Designer in WW row ARTB Column | xs
UX Improvements | H |  | ST-1955 | Updated SAS Calculation | What: Improve SAS Cal approach Why: Customer demand Outcome: Reduction in support calls | 1. SAS calculation changes | m
UX Improvements | H |  | ST-1955 | Increase RT | What: Increase max RT Why: Customer demand Outcome: Ability to plan for larger trials (i.e. covid) | 1. Increase RT to 150K | xs
UX Improvements | C |  | ST-1955 | Create Plans: R-type / S-type | What: Modify "create plan type" options Why: Streamline creation of R-type cohort plans Outcome: ability to create all 3 plans types without going into CDOS | 1. Create Plan – R-Type and S-Type Options | m
UX Improvements | H |  | ST-1955 | Parent cohort not defined - error msg | What: Improve error message handeling Why: accuratly Inform users of issue Outcome: Reduction in support calls | 1. Error Message - Parent Cohort Not completely defined | s
UX Improvements | M |  | ST-74 | Persisting User Selections | What: Maintian user selections / preferances Why: Customer demand Outcome: Better useability | 1. Study Tab - Enrollment View - persist hide/display selection of grid/graph view 2. Study Tab - Study Milestones - persist hide/display selection of grid/graph view 3. Study Tab - Reports - persist hide/display selection of grid/graph view 4. Country Tab - Country Performance - persist hide/display selection of grid view 5. Country Tab - Cohort Performance - persist hide/display selection of grid view 6. Multi-Country Edit - persist hide/display selection of grid view | s
Plan Adjustment Improvements | H |  | ST-1702 | Adjustment - abiliy to use approved plan rates | What: Ability to use approved plan rates in adjustments Why: Customer Demand Outcome: Ability to use approved plan rates in adjustments | 1. DCP view Reset Algorithm using Approved Plan values 2. MCE View - Reset Algorithm using Approved Plan values | m
Plan Adjustment Improvements | H |  | ST-1702 | FSS Date - when FSIV has occurred | What: Improve error message handeling Why: accuratly Inform users of issue Outcome: Reduction in support calls | 1. FSS Date - when FSIV has occurred | xs
Plan Adjustment Improvements | H |  | ST-1702 | Adjustment – MCS projected contributing sites < 1 | What: Improvement to Optimal Subject sovler Why: Customer demand Outcome: When< 1 site is projected to contribute, no error is thrown | 1. Adjustment – MCS projected contributing sites < 1 | s
Plan Adjustment Improvements | H |  | ST-1702 | Adjustment – MCS auto populate min # of sbj | What: Auto populate min sbj when actuals are present Why: Customer demand Outcome: | 1. Adjustment – MCS minimum # of subjects | xs
Plan Adjustment Improvements | H |  | ST-1702 | Adjustment – Solve for # of Subjects | What: Add subject solver to plan adjustment solvers Why: Customer demand Outcome: | 1. Adjustment – Solve for # of Subjects | m
Tech Debt | C |  | ST-5762 | Update export Excel Version | What: Upgrade reporting engine Why: To allow more than 256 column in an export Outcome: accurate exports | 1. Jasper report engine upgrade 2. Reports truncate after column IV (256 columns) | L (lots of testing)
[6 empty] | xs | 1w
[6 empty] | s | 2W
[6 empty] | M | 4W

## Goals
Goals for pre-planning:
1. Ensure we have broken out epics small enough to be (a) estimated and (b) accomplished in 2 - 3 sprints
2. Ensure we have all story stubs needed for estimation listed
3. Assign stack rank based on priority
Goals for in-planning:
1. T-shirt size the Epics
2. Identify dependencies that will inform sequencing
3. Identify teams that can perform the work
Goals for post-planning:
1. Wall Planning (i.e. resource planning to produce a roadmap)
2. Share roadmap internally with prod/dev team
3. Share roadmap internally with governance committee
4. Monthly updates (epic-level reporting)